## Instructions
# | Step
1 | Enter planned start of school date in cell D1 of "Detailed Checklist" sheet
2 | The due dates will automatically calculate in column E (do not delete formulas in these cells)
3 | To adjust the due dates if needed, change the number of days before school starts in column F

## Detailed Checklist
Microschool Opening Checklist |  | Opening Date: | 2026-08-10
(Planning Year)
Status | Category | Task | Owner | Due Date | Days Before Opening | Frequency | Microschool? | Notes | Specific FL Info
| Legal | Select Attorney | School Executive | 2024-11-28 | 620 |  | Yes
| Legal | Verify Corporation Name is Not Taken | School Executive | 2024-11-28 | 620 |  | Yes
| Operations | Obtain Mail Service/Mailbox | School Executive | 2024-11-28 | 620 |  | If Applicable
| Marketing | Finalize Advertising Strategy | School Executive | 2024-11-28 | 620 |  | Yes
| Marketing | Secure School Domain | School Executive | 2024-11-28 | 620 |  | Yes
| Marketing | Secure Most Likely URLs | School Executive | 2024-11-28 | 620 |  | Yes
| Legal | Create Articles of Incorporation | School Executive | 2024-11-29 | 619 |  | Yes
| Legal | Create Draft of Bylaws | School Executive | 2024-11-29 | 619 |  | Yes
| Compliance/Governance | Founder Approves Adopts Articles of Incorporation | School Executive | 2024-11-30 | 618 |  | Yes
| Compliance/Governance | Founder Approves Adopts Corporate Bylaws | School Executive | 2024-11-30 | 618 |  | Yes
| Legal | Incorporate Corporation | School Executive | 2024-12-01 | 617 |  | Yes
| Legal | Register Fictitious Name with State | School Executive | 2024-12-03 | 615 |  | If Applicable
| Food Service | Decide if school will participate in USDA program | SOM | 2024-12-08 | 610 |  | Yes
| Food Service | Determine state requirements to participate in the USDA NSLP program | SOM | 2024-12-10 | 608 |  | Yes
| Administrative | Submit Request for EIN | School Executive | 2024-12-17 | 601 |  | Yes
| Accounting/Finance | Apply for 501(c)(3) Status by Submiting IRS Form 1023 | School Executive | 2024-12-18 | 600 |  | If Applicable | If planning to be a non-profit
| Fundraising | Kickoff Fundraiser | School Executive | 2024-12-18 | 600 |  | Yes
| Marketing | Begin Creation of Temporary Website | School Executive | 2024-12-18 | 600 |  | Yes
| Operations | Discuss After-School program options | School Executive | 2024-12-18 | 600 |  | Yes
| Safety & Security | Select Security Approach | School Executive | 2024-12-18 | 600 |  | Yes
| Accounting/Finance | Receive 501(c)(3) Determination Letter | School Executive | 2025-02-26 | 530 |  | If Applicable | If planning to be a non-profit
| Accounting/Finance | Apply for Sales Tax Exemption | School Executive | 2025-02-26 | 530 |  | If Applicable | If planning to be a non-profit
| Marketing | Create Drafts of Possible Logos | School Executive | 2025-02-26 | 530 |  | Yes
| Marketing | Crate Direct Mail Art | School Executive | 2025-03-08 | 520 |  | Yes
| Marketing | Select Preliminary Logo | School Executive | 2025-03-08 | 520 |  | Yes
| Marketing | Obtain Final Logo Approval | School Executive | 2025-03-28 | 500 |  | Yes
| Marketing | Temporary Website "Go Live" | School Executive | 2025-03-28 | 500 |  | Yes
| Marketing | Create Pre-school Flyer | School Executive | 2025-03-28 | 500 |  | Yes
| Marketing | Develop a Public Relations plan | School Executive | 2025-03-28 | 500 |  | Yes
| Marketing | Website Development Meeting | School Executive | 2025-05-17 | 450 |  | Yes
| Marketing | Develop School Message | School Executive | 2025-06-16 | 420 |  | Yes
| Marketing | Create Information Meeting Plan and Lead Generation Strategy | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Create Marketing Materials | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Identify Location for Parent Info Meetings | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Create Schedule of Parent Info Meetings | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Update Website with Parent Meeting Plan | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Create Plan for Editorials from Supporters | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Create Advertising Budget for Enrollment | School Executive | 2025-07-06 | 400 |  | Yes
| Land/ Construction/ Building | Initiate Loan Process for Land Acquisition and Facility Construction (If Constructing Building) | School Executive | 2025-07-06 | 400 |  | If Applicable
| Operations | Reach consensus on Enrollment Plan | School Executive | 2025-07-06 | 400 |  | Yes
|  | Setup & Implement Enrollment System - Enrollment | School Executive | 2025-07-06 | 400 |  | Yes
| Enrollment | Enrollment Goal for Funding | School Executive | 2025-07-06 | 400 |  | Yes
| Human Resources | Initiate Principal/Head of School Search | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Approve Final School Logo Image for Website | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Launch Permanent Website | School Executive | 2025-07-06 | 400 |  | Yes
| Marketing | Post School Academic Calendar to School Website | School Executive | 2025-07-06 | 400 |  | Yes
| Land/ Construction/ Building | Make Initial Offer for Land or Building (If Constructing Building) | School Executive | 2025-07-06 | 400 |  | Yes
| Land/ Construction/ Building | Locate Building to Buy/Lease | School Executive | 2025-07-06 | 400 |  | Yes
| Land/ Construction/ Building | Confirm Zoned for Educational Use | School Executive | 2025-07-07 | 399 |  | Yes
| Land/ Construction/ Building | If Necessary, Initiate Re-Zoning Process | School Executive | 2025-07-08 | 398 |  | Yes
| Land/ Construction/ Building | Initiate Fire Inspection to Obtain a Fire Certificate | School Executive | 2025-07-09 | 397 |  | Yes
| Land/ Construction/ Building | Founder Approves Final Offer for Land or Building; Reached a deal); If Constructing Building | School Executive | 2025-07-26 | 380 |  | Yes
| Land/ Construction/ Building | Founder Approves and Signs Financing Documents; Closes on Loan; (If constructing building | School Executive | 2025-07-26 | 380 |  | Yes
| Land/ Construction/ Building | Secure Bond Financing (If Constructing Building) | School Executive | 2025-07-26 | 380 |  | Yes
| Land/ Construction/ Building | Create a Construction RFP and Specifications (If Constructing Building) | School Executive | 2025-08-05 | 370 |  | Yes
| Land/ Construction/ Building | Request Construction Bids (If Constructing Building) | School Executive | 2025-08-15 | 360 |  | Yes
| Enrollment | Create Enrollment Advertising Plan | School Executive | 2025-08-25 | 350 |  | Yes
| Enrollment | Create Paper Enrollment Application | School Executive | 2025-08-25 | 350 |  | Yes
| Enrollment | Create Consumer Email Art for Enrollment | School Executive | 2025-08-25 | 350 |  | Yes
| Enrollment | Create a Enrollment Tracking Spreadsheet | School Executive | 2025-08-25 | 350 |  | Yes
| Enrollment | Develop a Enrollment Marketing Plan | School Executive | 2025-08-25 | 350 |  | Yes
| Accounting/Finance | Create a Payment Mechanism on the Website Linked to the School Bank Account | School Executive | 2025-08-26 | 349 |  | Yes
| Enrollment | Send Enrollment Email to Interest Group | School Executive | 2025-08-26 | 349 |  | Yes
| Enrollment | Update Website with Enrollment Opening Information | School Executive | 2025-08-27 | 348 |  | Yes
| Enrollment | Provide Parent Meeting Proposed Locations to Marketing | School Executive | 2025-08-27 | 348 |  | Yes
| Enrollment | Add Parent Student Contract to Enrollment Software and Hard Copy Registration Package | School Executive | 2025-08-27 | 348 |  | Yes
| Enrollment | Open Enrollment Software Account | School Executive | 2025-08-27 | 348 |  | Yes
| Enrollment | Review Enrollment Process Description and Forms | School Executive | 2025-08-27 | 348 |  | Yes
| Enrollment | Setup Enrollment Calendars for Charter Application and Registration | School Executive | 2025-08-27 | 348 |  | Yes
| Enrollment | Configure Enrollment Software | School Executive | 2025-09-09 | 335 |  | Yes
| Land/ Construction/ Building | Obtain Construction Bids (If Constructing Building) | School Executive | 2025-09-14 | 330 |  | Yes
| Land/ Construction/ Building | Obtain Construction Builders Risk Insurance (If Constructing Building) | School Executive | 2025-09-14 | 330 |  | Yes
| Enrollment | Open Enrollment Software for Applications | School Executive | 2025-09-15 | 329 |  | Yes
| Land/ Construction/ Building | Evaluate Construction Contracts (If Constructing Building) | School Executive | 2025-09-24 | 320 |  | Yes
| Land/ Construction/ Building | Obtain Loan Commitment from Lender for Land and Construction Loan (If Constructing Building) | School Executive | 2025-09-24 | 320 |  | Yes
| Land/ Construction/ Building | Founder Approves "Best Value Bidder" Construction Contract Award (If Constructing Building) | School Executive | 2025-09-29 | 315 |  | Yes
| Human Resources | Hire a Principal | Board | 2025-10-01 | 313 |  | Yes
| Land/ Construction/ Building | Founder Signs Construction Contract (If Constructing Building) | School Executive | 2025-10-04 | 310 |  | Yes
| Human Resources | Hire a Registrar | School Executive | 2025-10-14 | 300 |  | Yes
| Marketing | Order Principal's Name Tag | School Executive | 2025-10-14 | 300 |  | Yes
| Compliance/Governance | Founder Approves Principal Hire | Board | 2025-10-14 | 300 |  | Yes
| Food Service | Create a Food Service Pacing Plan/Steps (Contact Optima for more information), If not using NSLP | SOM | 2025-10-14 | 300 |  | Yes
| Human Resources | Create Job Descriptions | School Executive | 2025-10-14 | 300 |  | Yes
| Marketing | Create Social Media Pages | School Executive | 2025-10-14 | 300 |  | Yes
| Marketing | Create & Utilize an Email System Account to Begin Collecting Emails | School Executive | 2025-10-14 | 300 |  | Yes
| Marketing | Create Palm Card; Print at Least 1000 | School Executive | 2025-10-14 | 300 |  | Yes
| Marketing | Add School to Email System | School Executive | 2025-10-14 | 300 |  | Yes
|  | Obtain Chamber membership | School Executive | 2025-10-14 | 300 |  | Yes
| Administrative | Obtain Builder's Risk Insurance Policy (If Constructing Building) | School Executive | 2025-10-14 | 300 |  | Yes
| Procurement | Establish Purchasing Process | School Executive | 2025-10-14 | 300 |  | Yes
| Procurement | Prepare a Technology RFP | School Executive | 2025-10-14 | 300 |  | Yes
| Procurement | Prepare an RFP for Furniture, Fixtures, & Equipment | School Executive | 2025-11-03 | 280 |  | Yes
| Accounting/Finance | Setup Bank Account (if not complete) | School Executive | 2025-12-03 | 250 |  | Yes
| Procurement | Request Technology Proposal from 3 Vendors | School Executive | 2025-12-03 | 250 |  | Yes
| Enrollment | Review and Verify Registration Packets (Registrar) | SOM | 2025-12-03 | 250 | Annually | Yes
| Operations | Obtain Founder approval of Technology Services Contract, if applicable | School Executive | 2025-12-23 | 230 |  | Yes
| Human Resources | Negotiate HR Company Contract If Applicable | School Executive | 2025-12-23 | 230 |  | Yes
| Human Resources | Create Staffing Plan | School Executive | 2025-12-23 | 230 |  | Yes
| Operations | Sign IT Technology Services Contract, if applicable | School Executive | 2026-01-02 | 220 |  | If Applicable
| Enrollment | Cross Train on Registration Process | School Executive | 2026-01-02 | 220 |  | Yes
| Enrollment | Initiate Student Registration | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Plan Staff Training | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Establish Background Check Procedures (Employees, Volunteers, vendors) | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Classical Job Fair Registrations | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Establish Employee Benefits | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Ensure that HR Attends Career Expos | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Contact Local Colleges Regarding Hiring Plans | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Establish Hiring Process | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Create Administrator Evaluation Procedures | School Executive | 2026-01-02 | 220 |  | Yes
| Marketing | Complete Conducting Informational Meetings | School Executive | 2026-01-02 | 220 |  | Yes
| Marketing | Recommend Events for School Event Calendar | School Executive | 2026-01-02 | 220 |  | Yes
| Procurement | Present Furniture Request List by Room with Principal/HOS Input | School Executive | 2026-01-02 | 220 |  | Yes
| Procurement | Update Equipment List By Room Per Principal's Direction | School Executive | 2026-01-02 | 220 |  | Yes
| Procurement | Setup Amazon Business Account for School | School Executive | 2026-01-02 | 220 |  | Yes
| Human Resources | Setup Portal to Human Resources System | HR | 2026-01-02 | 220 |  | Yes
| Human Resources | Reach Out to Local Colleges for Staff Recruitment | HR | 2026-01-02 | 220 |  | Yes
| Accounting/Finance | Market Student Supply Program | SOM | 2026-01-02 | 220 |  | Optional
| Administrative | Curriculum: Manage School Outyear Curriculum selection: 1. Analyze Recommendations 2. Evaluate New, Changed, Deleted Recommendations 3. Decide Each Grade Curriculum List | Principal | 2026-01-02 | 220 |  | Yes
| Human Resources | Create Cal-OSHA and OSHA Compliant Safety Handbook | HR | 2026-01-02 | 220 | As Required | Yes
| Administrative | Set Teacher Start Date for Academic Calendar | Principal | 2026-01-12 | 210 | Annually | Yes
| Procurement | Create Draft of Supplies to Purchase | School Executive | 2026-01-20 | 202 |  | Yes
| Procurement | Create Room Requirements for Technology | School Executive | 2026-01-20 | 202 |  | Yes
| Procurement | Create Technology Purchase Requirements for First 2 Years | School Executive | 2026-01-21 | 201 |  | Yes
| Accounting/Finance | Develop Financial Process for Purchasing | School Executive | 2026-01-22 | 200 |  | Yes
| Accounting/Finance | Create Recommendation for Authorized CHECK Signers | School Executive | 2026-01-22 | 200 |  | Yes
| Accounting/Finance | Create Recommendation for Authorized CONTRACT Signers | School Executive | 2026-01-22 | 200 |  | Yes
| Accounting/Finance | Create Salary Schedule | School Executive | 2026-01-22 | 200 |  | Yes
| Compliance/Governance | Founder Approves Insurance Contract | School Executive | 2026-01-22 | 200 |  | Yes
| Compliance/Governance | Founder Approves School Academic Calendar | School Executive | 2026-01-22 | 200 |  | Yes
| Compliance/Governance | Founder Approves Year 1 Staffing Plan | School Executive | 2026-01-22 | 200 |  | Yes
| Procurement | Create Initial Technology Order Plan | School Executive | 2026-01-22 | 200 |  | Yes
| School Documents | Create Parent Student Contract | School Executive | 2026-01-22 | 200 |  | Optional
| Human Resources | Confirm Retirement Program | School Executive | 2026-01-22 | 200 |  | Yes
| Human Resources | Organize New Hires Onboarding/Training | HR | 2026-01-22 | 200 |  | Yes
| Procurement | Create Initial Curriculum Bill of Materials | School Executive | 2026-01-22 | 200 |  | Yes
| Procurement | Meet with Selected IT Vendor to Discuss IT Technology Ceeds | School Executive | 2026-01-22 | 200 |  | Yes
| Procurement | Review Copy Machine Requirements | School Executive | 2026-01-22 | 200 |  | Yes
| Procurement | Specify initial equipment by room | School Executive | 2026-01-22 | 200 |  | Yes
| Marketing | Coordinate Groundbreaking (If Constructing Building) | School Executive | 2026-01-22 | 200 |  | If Applicable
| Technology | Review Online Systems Plan and Status | Principal | 2026-01-22 | 200 |  | Yes
| Compliance/Governance | Review Florida Public Records Request Statutes | Principal | 2026-01-22 | 200 |  | Yes
| Administrative | Recommend Dress Code/Uniforms | Principal | 2026-01-22 | 200 |  | Yes |  | 1002.33(17)(h) 1011.78
| Procurement | Obtain contract for Water - New Building Construction | SOM | 2026-01-22 | 200 |  | Yes
| Procurement | Obtain contract for Electric Power - New Building Construction | SOM | 2026-01-22 | 200 |  | Yes
| Facility Management | Discuss Classroom Setup Alternatives (Student Backs to Doormat) | Principal | 2026-01-22 | 200 |  | Yes
| Human Resources | Begin Interviewing Faculty Applicants | Principal | 2026-01-22 | 200 |  | Yes
| Administrative | Approve Process to Purchase Based on Curriculum; Review List and Create Plan | Principal | 2026-01-22 | 200 |  | Yes
| Procurement | Order Initial Curriculum Samples | School Executive | 2026-01-27 | 195 |  | Yes
| Human Resources | Hire a School Operations Manager (SOM) | Board or Principal | 2026-02-01 | 190 |  | Yes
| Compliance/Governance | Founder Completes Governance Training | School Executive | 2026-02-01 | 190 |  | Yes
| Human Resources | Founder Approves Staffing Plan | School Executive | 2026-02-01 | 190 |  | Yes
| Procurement | Specify Copy Machines Requirements | School Executive | 2026-02-01 | 190 |  | Yes
| Procurement | Develop Final Technology Plan | School Executive | 2026-02-01 | 190 |  | Yes
| Human Resources | Review Year 1 Salary Schedule | Principal | 2026-02-06 | 185 |  | Yes
| Administrative | Create Initial Daily Schedule | School Executive | 2026-02-11 | 180 |  | Yes
|  | Implement background screening policies and procedures | School Executive | 2026-02-11 | 180 |  | Yes
| Accounting/Finance | Provide Workers' Compensation Insurance Coverage | School Executive | 2026-02-11 | 180 |  | Yes
| Administrative | Initiate Transportation Solution Contract If Required | School Executive | 2026-02-11 | 180 |  | If Applicable
|  | Founder designates Records Custodian | School Executive | 2026-02-11 | 180 |  | Yes
| Procurement | Finalize Source for Lease of Printers & Copy Machines | School Executive | 2026-02-11 | 180 |  | Yes
| Enrollment | Founder Approves Annual Enrollment Capacity | School Executive | 2026-02-21 | 170 |  | Yes
| Compliance/Governance | Founder Approves Year 1 Salary Schedule | School Executive | 2026-02-26 | 165 |  | Yes
| Accounting/Finance | Create Preliminary Budget and Presentation | School Executive | 2026-03-13 | 150 |  | Yes
| Accounting/Finance | Create Marketing Budget | School Executive | 2026-03-13 | 150 |  | Yes
| Compliance/Governance | Founder Complete Background Checks | School Executive | 2026-03-13 | 150 |  | Yes
| Compliance/Governance | Founder Approves Staff Job Offers | School Executive | 2026-03-13 | 150 |  | Yes
| Compliance/Governance | Founder Approves Annual Instructional Staff Contracts | School Executive | 2026-03-13 | 150 |  | Yes
| Accounting/Finance | Establish School General Ledger Chart of Accounts | School Executive | 2026-03-13 | 150 |  | Yes
| Accounting/Finance | Establish Special Purpose Entities Chart of Accounts | School Executive | 2026-03-13 | 150 |  | Yes
| Food Service | Direct Certified (DC) File | School Executive | 2026-03-13 | 150 |  | If Applicable | If plannin to participate in NSLP program
| Food Service | District or Authorizing Agency Agreement and Attestation Form | School Executive | 2026-03-13 | 150 |  | If Applicable | If plannin to participate in NSLP program
| Food Service | Direct Certification Agreement | School Executive | 2026-03-13 | 150 |  | If Applicable | If plannin to participate in NSLP program
| Food Service | Meal Counting and Claiming Procedures | SOM | 2026-03-13 | 150 |  | If Applicable | If plannin to participate in NSLP program
| Food Service | Food Safety Plan (HACCP)) | School Executive | 2026-03-13 | 150 |  | If Applicable | If plannin to participate in NSLP program
| Accounting/Finance | Create a Procurement Policy | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement Asset Mgt System | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement SIS System | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement Classroom Observation & Evaluation System | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement Learning Systems (Assessment &/or Instruction Programs)- I-Ready, IXL, Dibels, Spire | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement Food Service Systems (POS, App, Verification, Pmt), If applicable | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement Group Organizing System (SignUpGenius) | School Executive | 2026-03-13 | 150 |  | Yes
|  | Setup & Implement Mobile Panic Alert System | School Executive | 2026-03-13 | 150 |  | Yes
|  | Add school to Policy/Procedure/Process Management System (Sweet Process) | School Executive | 2026-03-13 | 150 |  | Optional
|  | Add school to Online Training System (Medication, Mental Health, etc.) - SafeSchools/Vector | School Executive | 2026-03-13 | 150 |  | Optional
|  | Add school to Project Management System | School Executive | 2026-03-13 | 150 |  | Optional
|  | Contact bus companies, if applicable | School Executive | 2026-03-13 | 150 |  | Yes
| Procurement | Provide Final Curriculum Bill of Materials | School Executive | 2026-03-13 | 150 |  | Yes
| Procurement | Order Furniture | School Executive | 2026-03-13 | 150 |  | Yes
| Before & After School Care | Finalize Before and After School Care Program | SOM | 2026-03-13 | 150 |  | Yes
| Administrative | Develop Uniform Dress Code Description and Pictures for Website | SOM | 2026-03-13 | 150 |  | Yes
| Procurement | Order Grant Funded technology | School Executive | 2026-03-23 | 140 |  | Yes
| Procurement | Select Student Planner Design | Principal | 2026-03-31 | 132 |  | Yes
| Procurement | Order initial Curriculum Large Orders for Semester 1; 2 if Budget Permits) | School Executive | 2026-04-12 | 120 |  | Yes
| Administrative | Obtain Student Transportation Services Quotes | School Executive | 2026-04-12 | 120 |  | If Applicable | If planning to provide bus service
| Compliance/Governance | Founder Reviews Preliminary Budget | School Executive | 2026-04-22 | 110 |  | Yes
|  | Create Class Schedule and Review with Principal. See Optima for template | School Executive | 2026-05-02 | 100 |  | Yes
| Compliance/Governance | Founder Approves Conflict of Interest Policy | School Executive | 2026-05-02 | 100 |  | Yes
| Compliance/Governance | Founder Approves Non-Discrimination Resolution | School Executive | 2026-05-02 | 100 |  | Required if Non-Profit | 2000 EO CPE Text
| Compliance/Governance | Founder Completes Conflict of Interest form | School Executive | 2026-05-02 | 100 |  | Optional
| Compliance/Governance | Include Non-Discrimination Statement on Website if School is Non-Profit | School Executive | 2026-05-02 | 100 |  | Required if Non-Profit |  | 27 CFR 601.201: Rulings and determination letters. Rev. Proc. 2019-22
| Administrative | Provide Private Transportation Options | School Executive | 2026-05-02 | 100 |  | If Applicable | If planning to provide bus service
| Administrative | Finalize Uniform Policy | SOM | 2026-05-02 | 100 |  | Yes
|  | Obtain contract for Dismissal System or License Plate Reader System | School Executive | 2026-05-02 | 100 |  | Yes
|  | Complete Systems Checklist to Assess Needs | School Executive | 2026-05-02 | 100 |  | Yes
|  | Work with Accounting to Request Systems Needed for School | School Executive | 2026-05-02 | 100 |  | Yes
|  | Create Before/Aftercare Parent Handbook | School Executive | 2026-05-02 | 100 |  | Yes
| Administrative | Complete insurance applications | School Executive | 2026-05-02 | 100 |  | Yes
| Procurement | Founder Approves Vendor Contracts | School Executive | 2026-05-02 | 100 |  | Yes
| Procurement | Order Initial Technology | School Executive | 2026-05-02 | 100 |  | Yes
| School Documents | Create Student Progression Plan | School Executive | 2026-05-02 | 100 |  | Yes
| Enrollment | Student Local Tracking Database Configured (Registrar) | SOM | 2026-05-02 | 100 |  | Yes
| Enrollment | Setup Registrar to Enter Student Data into SIS system | SOM | 2026-05-02 | 100 |  | Yes
| Administrative | Select Samples of Textbooks to Review | Principal | 2026-05-02 | 100 |  | Yes
| Technology | Review Lesson Plan System | Principal | 2026-05-02 | 100 |  | Yes
| Academics | Plan PE Curriculum (Curriculum Coordinator) | Principal | 2026-05-02 | 100 |  | Yes
| Human Resources | Interview Non-Faculty Applicants | SOM | 2026-05-02 | 100 |  | Yes
| Academics | Curriculum Specifics Content Update If Required; Decide Which Books to Cover in Sequence; Select 1st Semester Textbooks | Principal | 2026-05-02 | 100 |  | Yes
| Administrative | Create Yearbook Program - Recruit Yearbook Manager/Producer | School Executive | 2026-05-02 | 100 | As Required | Yes
| Enrollment | Configure SIS: Enter all student schedules, bells, and periods in SIS from School SIS or what Enrollment Manager provides. (Yearly maintenance and can be changed at any given time with new hires or ESE services) | Registrar | 2026-05-02 | 100 | As Required | Yes
| Procurement | Approve Draft Classroom and Student Supplies to Purchase | Principal | 2026-05-02 | 100 |  | Yes
| Procurement | Approve Draft Classroom and Student Supplies List | Principal | 2026-05-02 | 100 |  | Yes
| Human Resources | Hire Administrative Assistant (Starts Sooner Than Others) | Principal | 2026-05-12 | 90 |  | Yes
| Administrative | Create Insurance Contract Evaluation Presentation for Founder | School Executive | 2026-05-17 | 85 |  | Yes
| Academics | Work with Uniform Supplier to Setup Account and Marketing Material | SOM | 2026-05-22 | 80 |  | Yes
| Safety & Security | Obtain Operations Manager's Approval of Crisis Response Plan | School Executive | 2026-05-22 | 80 |  | Optional
| Administrative | Yearbook - Program Advisor and Coordination with Company | School Executive | 2026-05-22 | 80 |  | Yes
| Human Resources | Plan New Hire Orientation Meeting | SOM | 2026-05-22 | 80 |  | Yes
| Procurement | Order Student Planners (in concert with principal) | SOM | 2026-05-22 | 80 |  | Yes
| Procurement | Issue setup of Utilities Connection and setup Monthly payments: Coordinate with construction company Builder will not be coordinating Internet & cable | SOM | 2026-05-22 | 80 |  | Yes
| Human Resources | Hire Security Guard | SOM | 2026-05-22 | 80 |  | Yes
| Human Resources | Hire Receptionist | SOM | 2026-05-22 | 80 |  | Yes
| Human Resources | Hire Ops Specialists | SOM | 2026-05-22 | 80 |  | Yes
| Human Resources | Hire Health & Wellness Coordinator | SOM | 2026-05-22 | 80 |  | Yes
| Human Resources | Hire Facility Manager | SOM | 2026-05-22 | 80 |  | Yes
| Human Resources | Hire Day Porters | SOM | 2026-05-22 | 80 |  | Yes
| Enrollment | Evaluate Registration for ESE Needs (SSD Director) | Principal | 2026-05-22 | 80 |  | Yes
| School Documents | Complete Editorial Review of All School Documents | School Executive | 2026-05-27 | 75 |  | Yes
| Safety & Security | Create Draft Active Assailant Response Plan | School Executive | 2026-05-27 | 75 |  | Optional
|  | Complete Peer Review of Student Code of Conduct | School Executive | 2026-05-27 | 75 |  | Yes
| Administrative | Finalize Insurance Policies | School Executive | 2026-06-01 | 70 |  | Yes
| Safety & Security | Complete Editorial Review of Active Assailant Response Plan | School Executive | 2026-06-01 | 70 |  | Optional
| Compliance/Governance | Founder Approves Check Signing Responsibility | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Founder Approves Policy Manual | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Founder Approves Final Budget in June | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Founder Approves Authorized Contract Signers | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Setup Staff Email Accounts | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Founder Obtains Unsecured Loan or Donation for Startup | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Confirm Founder Conflict of Interest Status | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Complete Founder Fingerprinting | School Executive | 2026-06-01 | 70 |  | Yes
| Facility Management | Create Initial Asbestos Management Plan | School Executive | 2026-06-01 | 70 |  | Yes
| Operations | Create dismissal policies and procedures | School Executive | 2026-06-01 | 70 |  | Yes
| Safety & Security | Create Draft Crisis Response Plan | School Executive | 2026-06-01 | 70 |  | Optional
| School Documents | Create Parent-Student Handbook | School Executive | 2026-06-01 | 70 |  | Yes
| School Documents | Create Student Code of Conduct | School Executive | 2026-06-01 | 70 |  | Yes
|  | Create Founder Report of School's Progress | School Executive | 2026-06-01 | 70 |  | Yes
|  | Monthly: Create monthly note payments; log in amortization schedule | School Executive | 2026-06-01 | 70 |  | Yes
| Compliance/Governance | Code of Student Conduct is Ready for Founder Approval | School Executive | 2026-06-01 | 70 |  | Optional
| Compliance/Governance | Create Founder and Admin Clearance Process | School Executive | 2026-06-01 | 70 |  | Optional
| Accounting/Finance | Establish Fixed Asset Schedules and Depreciation Reports by Fund/Function/Account/Location | School Executive | 2026-06-01 | 70 |  | Yes
|  | Setup & Implement Substitute Teacher Management System | School Executive | 2026-06-01 | 70 |  | Yes
|  | Setup & Implement Visitor Management System (SafeVisitor) | School Executive | 2026-06-01 | 70 |  | Optional
|  | Setup & Implement School Dismissal System | School Executive | 2026-06-01 | 70 |  | Yes
| Academics | Create Uniform Policy | Principal | 2026-06-01 | 70 |  | Yes
|  | Create a Health Clinic Manual Request District or Authorizing Agency or County Health Handbook | School Executive | 2026-06-01 | 70 |  | Yes
|  | Archive documentation of approval to use facility | School Executive | 2026-06-01 | 70 |  | Yes
|  | Fingerprinting of Founder, Staff and Vendors | School Executive | 2026-06-01 | 70 |  | Yes
|  | Establish agreement with supplier for Floor Cleaning Chemical Dispensers | School Executive | 2026-06-01 | 70 |  | Yes
|  | Procure Asset Management System | School Executive | 2026-06-01 | 70 |  | Optional
|  | Develop training program for new systems | School Executive | 2026-06-01 | 70 |  | Yes
|  | Obtain Principal approval of Section scheduling | School Executive | 2026-06-01 | 70 |  | Yes
|  | Obtain Founder approval of First Year Board Meeting Schedule (Date and Time) | School Executive | 2026-06-01 | 70 |  | Yes
|  | Confirm that required Pre-Opening emails are sent | School Executive | 2026-06-01 | 70 |  | Yes
|  | Notify Parents of Accreditation Status | School Executive | 2026-06-01 | 70 |  | Yes
| Facility Management | Establish Agreement with Supplier for Restroom Dispensers | School Executive | 2026-06-01 | 70 |  | Optional
| Facility Management | Secure Facility | School Executive | 2026-06-01 | 70 |  | Yes
| Facility Management | Confirm Radon Testing & Reporting by Operations Manager | School Executive | 2026-06-01 | 70 |  | Yes
| Operations | Develop Parent Drop-off Traffic Flow | School Executive | 2026-06-01 | 70 |  | Yes
| Safety & Security | Founder Approves Crisis Response Plan | School Executive | 2026-06-01 | 70 |  | Optional
| Compliance/Governance | Founder Approves Code of Student Conduct | School Executive | 2026-06-01 | 70 |  | Yes
| Procurement | Order Equipment | School Executive | 2026-06-01 | 70 |  | Yes
| Procurement | Review Equipment by Room; Provide Suggestions; Use Equipment Requirement Spreadsheet | SOM | 2026-07-11 | 30 |  | Yes
| Procurement | Review and Provide Input of Furniture Order List By Room | Principal | 2026-07-11 | 30 |  | Yes
| Human Resources | Review Staffing Plan | Principal | 2026-07-11 | 30 | Annually | Yes
| Academics | Approve Master Schedule and Teacher Assignment | Principal | 2026-07-11 | 30 |  | Yes
| Administrative | Standardize Classroom Wall Operatives: Keep Distracting Clutter to Minimum | School Executive | 2026-06-01 | 70 | As Required | Yes
|  | Radon Testing and Reporting | SOM | 2026-06-01 | 70 |  | Yes |  | SOM must report results of Radon Testing http://www.floridahealth.gov/environmental-health/radon/ http://www.floridahealth.gov/environmental-health/radon/mandatory-testing.html http://www.floridahealth.gov/environmental-health/radon/radon-menu.html Obtain the Report from the Construction Company Send report to: HSEC_RadonReports@flhealth.gov https://404.056 Environmental radiation standards and projects; certification of persons performing measurement or mitigation services; mandatory testing; notification on real estate documents; rules (4) MANDATORY TESTING.—All public and private school buildings or school sites housing students in kindergarten through grade 12; all state-owned, state-operated, state-regulated, or state-licensed 24-hour care facilities; and all state-licensed day care centers for children or minors which are located in counties designated within the Department of Business and Professional Regulation’s Florida Radon Protection Map Categories as “Intermediate” or “Elevated Radon Potential” shall be measured to determine the level of indoor radon, using measurement procedures established by the department. Initial measurements shall be conducted in 20 percent of the habitable first floor spaces within any of the regulated buildings and shall be completed and reported to the department within 1 year after the date the building is opened for occupancy or within 1 year after license approval for the entity residing in the existing building. Follow-up testing must be completed in 5 percent of the habitable first floor spaces within any of the regulated buildings after the building has been occupied for 5 years, and results must be reported to the department by the first day of the 6th year of occupancy. After radon measurements have been made twice, regulated buildings need not undergo further testing unless significant structural changes occur. No funds collected pursuant to s. http://www.leg.state.fl.us/statutes/index.cfm?App_mode=Display_Statute&Search_String=&URL=0500-0599/0553/Sections/0553.721.html shall be used to carry out the provisions of this subsection.
| Administrative | Publish Bullying Policy Per Policy | Principal | 2026-06-01 | 70 |  | Yes
| Administrative | Plan and Implement Literacy Boot Camp for New K-3 Students: 1. Add to Calendar 2. Create Signup Form 3. Notify Parents 4. Plan Staff Participation 5. Coordinate Facility Usage 6. Conduct Event | Principal | 2026-06-01 | 70 |  | Yes
| Administrative | Plan and Implement Kindergarten Round Up: 1. Add to Calendar 2. Create Signup Form 3. Notify Parents 4. Plan Staff Participation 5. Coordinate Facility Usage 6. Conduct Event | Principal | 2026-06-01 | 70 |  | Yes
| Procurement | Perform Textbook Inventory (Curriculum Coordinator); Must Create Delivery Packages Per Classroom | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Yearbook and Pictures | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Visitor Management System | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Trash Removal | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Security Monitoring | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Recycle Removal | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Landscaping (Lawn, Bushes, Blowing & Fertilizing) | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Fire Sprinkler System Inspection | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Fire Alarm Monitoring | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for ESE Speech Consultant | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for ESE Psychologist Consultant | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Custodian Service | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Car Line System | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain contract for Pest Control company | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Obtain agreement of Supply Company for Dispensers for new building only? | SOM | 2026-06-01 | 70 |  | Yes
| Accounting/Finance | Market Classroom Supply Program | SOM | 2026-06-01 | 70 |  | Yes
| Academics | Initiate Lesson Plan Development by Teachers As They Are Hired | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Spanish Teachers | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Physical Education Teachers: K-6 Certified | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Music Teachers | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Latin Teacher | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire K-6 Teachers | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Exceptional Education Director | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire ESE Teachers | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Assistant Principal | Principal | 2026-06-01 | 70 |  | Yes
| Human Resources | Hire Art Teachers | Principal | 2026-06-01 | 70 |  | Yes
| Procurement | Find handyman for minor work at school | SOM | 2026-06-01 | 70 |  | Yes
| Safety & Security | Ensure That All Vendors Are Checked Against Jessica Lunsford Act | SOM | 2026-06-01 | 70 |  | Yes
| Administrative | Discuss Bullying Policy Per Policy at an Assembly | Principal | 2026-06-01 | 70 |  | Yes
| Accounting/Finance | Develop Reading Plan | Principal | 2026-06-01 | 70 | Annually | Yes
| Human Resources | Decide If We Post Qualification of Teachers on their Web Pages; Ask Principal; Headhunters Can Target Them | SOM | 2026-06-01 | 70 |  | Yes
| Human Resources | Create Website Accounts for New Staff | SOM | 2026-06-01 | 70 |  | Yes
| Safety & Security | Create Threat Assessment Team | SOM | 2026-06-01 | 70 |  | Yes |  | FS 1006.07 (6) (c) Annually (c) Each district school board and charter school governing board must adopt an active assailant response plan. By October 1, 2019, and annually thereafter, each district school superintendent and charter school principal shall certify that all school personnel have received annual training on the procedures contained in the active assailant response plan for the applicable school district or charter school.
| Administrative | Create and Publish Behavioral Expectations Per Policy | Principal | 2026-06-01 | 70 |  | Yes
| Extracurriculars | Create and Market After School Sports; Approval of Principal for Teacher Participation | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Window Cleaning | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Water/Sewer | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Sign Repairs | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Roof Repairs & Maintenance (R&M) | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Pressure Cleaning Building, Sidewalk and Signage | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Plumbing R&M | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Parking Lot Lighting R&M | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Mold Testing | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Lock and Key | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Landscape Fertilizing | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Fire Sprinkler System R&M | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Fire Extinguisher Annual Inspection | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Fire Alarm System R&M Service | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Fire Alarm System Annual Certification | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Exterior Lighting Maintenance | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Elevator R&M | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Elevator Preventive Maintenance and R&M (can wait) | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Elevator License | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Elevator Annual Inspection | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Electrical R&M | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Copy Machines Lease | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Building Exterior R&M (can wait) | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with Asphalt R&M (can wait) | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Contract with A/C Service Contract and R&M | SOM | 2026-06-01 | 70 |  | Yes
| Human Resources | Confirm Teachers Certification Is On Track | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Approve Draft Office and Facility Supplies to purchase | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Approve Draft Office and Facility Supplies list | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Accept Textbook Delivery (Curriculum Coordinator): Must Inventory and Sign Invoice for Payment | SOM | 2026-06-01 | 70 |  | Yes
| Procurement | Accept Supplies Deliveries. Need to create delivery packages per classroom. Must inventory and sign Invoice for payment | SOM | 2026-06-01 | 70 |  | Yes
| School Documents | Upload Required School Documents on Website Upon Founder's Approval | School Executive | 2026-06-06 | 65 |  | Yes
| School Documents | Founder Approves Student Progression Plan | School Executive | 2026-06-11 | 60 |  | Yes
| Safety & Security | Founder Approves Active Assailant Response Plan | School Executive | 2026-06-11 | 60 |  | Optional
| Compliance/Governance | Upload Code of Student Conduct on Website Upon Founder's Approval | School Executive | 2026-06-11 | 60 |  | Yes
| Procurement | Complete a Textbook Inventory | SOM | 2026-06-11 | 60 |  | Yes
| School Documents | Upload Student Progression Plan to Website | School Executive | 2026-06-12 | 59 |  | Yes
| Academics | Approve School Academic Calendar Submission to Founder | Principal | 2026-07-06 | 35 | Annually | Yes
| Accounting/Finance | Create Final Budget and Presentation | School Executive | 2026-06-21 | 50 |  | Yes
| Procurement | Order Final Technology That May Be Required | School Executive | 2026-06-21 | 50 |  | Yes
| Human Resources | Review, Edit and Approve Student Remediation Strategy | Principal | 2026-06-21 | 50 |  | Yes
| Administrative | Sign Insurance Forms | School Executive | 2026-07-01 | 40 |  | Yes
| Operations | Receive Ordered Technology | School Executive | 2026-07-01 | 40 |  | Yes
|  | Furniture Delivery and Installation Begins | School Executive | 2026-07-01 | 40 |  | Yes
| Procurement | Order Initial Math Manipulatives Supplies | School Executive | 2026-07-01 | 40 |  | Yes
| Procurement | Order Initial Science Supplies | School Executive | 2026-07-01 | 40 |  | Yes
| Procurement | Order Initial Office & Classroom Supplies | School Executive | 2026-07-01 | 40 |  | Yes
| Procurement | Order Classroom and Student Supplies | School Executive | 2026-07-01 | 40 |  | Yes
| Procurement | Order Office and Facility Supplies | School Executive | 2026-07-01 | 40 |  | Yes
| Operations | Inventory Received Technology | School Executive | 2026-07-03 | 38 |  | Yes
| Land/ Construction/ Building | Construction is Completed (If Constructing Building) | School Executive | 2026-07-11 | 30 |  | If Applicable | If building or some construction
|  | Coordinate First Staff Training | School Executive | 2026-07-11 | 30 |  | Yes
| Operations | Set Up Mail to School Address | School Executive | 2026-07-11 | 30 |  | Yes
|  | Review Year 1 Founder Approved Staffing Plan | Principal | 2026-07-11 | 30 |  | Yes
| Accounting/Finance | As required: Provide Input to Budget Process | SOM | 2026-07-11 | 30 | Annually | Yes
| Accounting/Finance | As required: Provide Input to Budget Process | Principal | 2026-07-11 | 30 | Annually | Yes
| Safety & Security | Review and Approve Crisis Response Plan | SOM | 2026-07-31 | 10 |  | Yes
| Human Resources | Work With IT to Create School Folders for Departments and Staff If Applicable | SOM | 2026-07-11 | 30 |  | Yes
| Human Resources | Work With IT to Add New Staff to Files/Drive | SOM | 2026-07-11 | 30 |  | Yes
| Human Resources | Work With IT on Creating Email Accounts for New Staff | SOM | 2026-07-11 | 30 |  | Yes
| Enrollment | Update Student Database with Registrations (Registrar) | SOM | 2026-07-11 | 30 | Annually | Yes
| Human Resources | Start-Up Services (Complete Service to Set Up New School Overhead) | HR | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Wi-Fi system | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Safety & Security | Setup and Configure Visitor Screening Application | SOM | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Switches | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Staff Microsoft Office | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Staff G-Suite Email system | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Staff Computers - UPS | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Staff Computers - Laptops | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Staff Computers - iPads | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Staff Computers - Desktops | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Servers | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Security: Virus Protection | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Security: Patching Process | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Security: Password Policies | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Security: Internal Security | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Public Address System | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Office Fax/Monochrome Printers | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Office Color Printers | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Office Check Printers | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Internet Access | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Hardware Server (Authentication, Print Server, etc.) | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure G-Suite Users | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure G-Suite Data Storage | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Facility Management | Setup and Configure Copiers | SOM | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Classroom Projectors | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Car Line Sound System | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Cameras -Hallway | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Cameras - Server software | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Cameras - External | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Camera - Hardware | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure Cafeteria Projector | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Technology | Setup and Configure VOIP phone System | SOM/IT | 2026-07-11 | 30 | As Required | Yes
| Administrative | Review Biomedical Waste Operating Plan for Clinic | SOM | 2026-07-11 | 30 |  | Yes
| Enrollment | Request Student Records (Registrar) | SOM | 2026-07-11 | 30 |  | Yes
| Procurement | Receive and Sign for Furniture Delivery and Installation; Must Inventory and Sign Invoice for Payment | SOM | 2026-07-11 | 30 |  | Yes
| Procurement | Receive and Sign for Equipment | SOM | 2026-07-11 | 30 |  | Yes
| Administrative | Post Prominently the Contact Information for the Agency's Custodian of Public Records in the in Front Lobby | SOM | 2026-07-11 | 30 |  | Optional |  | FS 119.12 (2)
| Administrative | Post Notice Stating That a Student's Locker or Other Storage Area is Subject to Search | SOM | 2026-07-11 | 30 |  | Optional |  | FS 1006.09(9) (9) A school principal or a school employee designated by the principal, if she or he has reasonable suspicion that a prohibited or illegally possessed substance or object is contained within a students locker or other storage area, may search the locker or storage area. The district school board shall require and each school principal shall cause to be posted in each public K-12 school, in a place readily seen by students, a notice stating that a students locker or other storage area is subject to search, upon reasonable suspicion, for prohibited or illegally possessed substances or objects.
| Administrative | Post Curriculum: Update Map on School Website per Policy | Principal | 2026-07-11 | 30 |  | Optional
| Administrative | Place Child Abuse Poster in Sschool | SOM | 2026-07-11 | 30 |  | Yes |  | FS 1006.061(4)(a)
| Facility Management | Obtain Health Certificate | SOM | 2026-07-11 | 30 |  | Yes
| Facility Management | Obtain Fire Inspection; Keep for records | SOM | 2026-07-11 | 30 |  | Yes
| Facility Management | Obtain Facility Health Inspection from County Health; Keep for records | SOM | 2026-07-11 | 30 |  | Yes
| Safety & Security | Obtain Contract for Staff Badges; Will Help Teachers Get Discounts | SOM | 2026-07-11 | 30 |  | Yes
| Administrative | Obtain Certificate of Occupancy from Builder | SOM | 2026-07-11 | 30 |  | Yes
| Land/ Construction/ Building | Obtain Asbestos Inspection and Certificate from Builder | SOM | 2026-07-11 | 30 |  | Yes
| Technology | Install VOIP System | SOM/IT | 2026-07-11 | 30 |  | Yes
| Safety & Security | Install Visitor Control System | SOM | 2026-07-11 | 30 |  | Yes
| Technology | Install Switches | SOM/IT | 2026-07-11 | 30 |  | Yes
| Technology | Install Servers | SOM/IT | 2026-07-11 | 30 |  | Yes
| Technology | Install Security Cameras | SOM/IT | 2026-07-11 | 30 |  | Yes
| Facility Management | Install Protective Slides On All Desks and/or Chairs to Protect Floors | SOM | 2026-07-11 | 30 | As Required | Yes
| Technology | Install PA System | SOM/IT | 2026-07-11 | 30 |  | Yes
| Technology | Install Networking Technology | SOM/IT | 2026-07-11 | 30 |  | Yes
| Technology | Install Internet Router | SOM/IT | 2026-07-11 | 30 |  | Yes
| Human Resources | Hire Two Recess Monitors 8 Hours a Day (Could Be Stay at Home Parents) | Principal | 2026-07-11 | 30 |  | Yes
| Human Resources | Hire Seven K-6 Instructional Assistants 8 Hours a Day (could be stay at home parents) | Principal | 2026-07-11 | 30 |  | Yes
| Human Resources | Hire Physical Education Assistants 4 Hours a Hay (could be stay at home parents) | Principal | 2026-07-11 | 30 |  | Yes
| Land/ Construction/ Building | Finalize Asbestos Management Plan | SOM | 2026-07-11 | 30 |  | Yes
| Administrative | Develop Day One Procedures | SOM | 2026-07-11 | 30 |  | Yes
| Safety & Security | Create Student Badge If Applicable | SOM | 2026-07-11 | 30 |  | Yes
| Procurement | Contract with ESE Consultants | SOM | 2026-07-11 | 30 |  | Yes
| Technology | Configure staff computers | SOM/IT | 2026-07-11 | 30 |  | Yes
| Safety & Security | Complete FSSAT | SOM | 2026-07-11 | 30 |  | Yes
| Land/ Construction/ Building | Assign a Staff to Serve as the School Asbestos Coordinator per Policy. Ensure He/She is Trained | SOM | 2026-07-11 | 30 |  | Yes
| Administrative | Approve Bus Routes by July 30 Per Policy | SOM | 2026-07-11 | 30 |  | Yes
| Technology | Accept and sign for Technology Delivery | SOM/IT | 2026-07-11 | 30 |  | Yes
|  | Obtain Principal approval of Elementary Student Assignments to Course Schedule | School Executive | 2026-07-21 | 20 |  | Yes
| Academics | Support Kindergarten Roundup | SOM | 2026-07-21 | 20 |  | Yes
| Human Resources | Staff are Fingerprinted and Cleared | HR | 2026-07-21 | 20 |  | Yes
| Academics | Decide on IXL Use for Math Remediation; Each Student Has An Account; Could Have After School Club | Principal | 2026-07-21 | 20 |  | Yes
| Facility Management | Tailor Certification Procedures for County Unique Requirements | School Executive | 2026-07-26 | 15 |  | Yes
| Academics | Review and Approve Kindergarten Roundup Plan: Just Prior to Start of School to Decide Which Kids to Separate | Principal | 2026-07-26 | 15 |  | Yes
| Academics | Conduct Kindergarten Roundup (Just Prior to Start of School to Decide Which Kids to Separate) | Principal | 2026-07-27 | 14 |  | Yes
| Administrative | Enroll School in Scripps Spelling Bee | School Executive | 2026-07-31 | 10 |  | Yes
| Administrative | Request Copies of Principal's Teacher Training Materials | School Executive | 2026-07-31 | 10 |  | Yes
|  | Procure IXL account | School Executive | 2026-07-31 | 10 |  | Yes
|  | Enter Students into SIS | School Executive | 2026-07-31 | 10 |  | Yes
|  | Enter Student Schedule Assignments into SIS | School Executive | 2026-07-31 | 10 |  | Yes
| Human Resources | Founder Approves Staff Evaluation System | School Executive | 2026-07-31 | 10 |  | Yes
| School Documents | Review and Comment on Student Progression Plan | Principal | 2026-08-08 | 2 | Annually | Yes
| Administrative | Ensure that Student Progression Plan is Uploaded to Website | SOM | 2026-08-08 | 2 |  | Yes
| Administrative | Start Teacher Orientation | Principal | 2026-07-31 | 10 |  | Yes
| Administrative | Setup Employment Posters on Bulletin Boards | SOM | 2026-07-31 | 10 | As Required | Yes
| Administrative | Reporting progress toward meeting the school's goals and objectives to the Founder | Principal | 2026-07-31 | 10 |  | Yes |  | FS 1002.33(9)(k)
| Enrollment | Receive Student Records (Registrar) | SOM | 2026-07-31 | 10 |  | Yes
| Administrative | Post Required Human Resources Notices in Teacher Workrooms 1. Employee Rights Under the Fair Labor Standards Act 2. Job Safety and Health: It's the Law 3. Employee Rights and Responsibilities Under The Family and Medical Leave Act 4. Pay Transparency Nondiscrimination Provision (41 CFR Part 60-1.3 | SOM | 2026-07-31 | 10 | As Required | Yes
| Academics | Plan to have Certified PE instructor review PE curricula and programs | Principal | 2026-07-31 | 10 |  | Yes |  | FS 1003.455
| Administrative | Notify parents of PE Opt-Out options | Principal | 2026-07-31 | 10 |  | Yes |  | FS 1003.455
| Facility Management | Install Room/Teacher Signage | SOM | 2026-07-31 | 10 |  | Yes
| Administrative | Install Clocks in Classrooms (If Required) | SOM | 2026-07-31 | 10 |  | Yes
| Facility Management | If Leasing - Rekey All Doors | SOM | 2026-07-31 | 10 |  | Yes
| Academics | Have Certified PE Instructor Review PE Curricula and Programs | Principal | 2026-07-31 | 10 |  | Yes |  | FS 1003.455
| Enrollment | Enter Student Data Into SIS system (Registrar) | SOM | 2026-07-31 | 10 |  | Yes
| Facility Management | Display of the State Motto, "In God We Trust," in Front Lobby | SOM | 2026-07-31 | 10 |  | Yes |  | FS 1003.45
| Safety & Security | Create Team for Early Warning System | Principal | 2026-07-31 | 10 |  | Yes |  | FS 1001.42 (18)(b)
| Extracurriculars | Create and Market After School Clubs | SOM | 2026-07-31 | 10 | As Required | Yes
| Operations | Manage Locker/Cubby Assignments 1. Assign by Homeroom and Gender 2. Update as required 3. Provide assignment lists to staff | SOM | 2026-07-31 | 10 |  | Yes
| Administrative | Teachers Prepare Classrooms | Principal | 2026-08-07 | 3 |  | Yes
| Enrollment | Conduct Open House for Parents | Principal | 2026-08-07 | 3 |  | Yes
| Enrollment | Conduct Open House | Principal | 2026-08-07 | 3 |  | Yes
| Academics | Conduct Kindergarten Roundup (Just Prior to Start of School to Decide Which Kds to Separate) | SOM | 2026-08-08 | 2 |  | Yes
| Administrative | Plan and Implement Kindergarten Open House 1. Add to Calendar 2. Prepare Student Class Sheets 3. Notify Parents 4. Plan Staff Participation 5. Coordinate Facility Usage 6. Conduct Event Principal Provides Direction | Principal | 2026-08-08 | 2 |  | Yes
| Administrative | Conduct Initial Before School Staff Training | Principal | 2026-08-09 | 1 | Annually | Yes
| Safety & Security | Confirm that Certified Training on the Procedures Contained in the Active Assailant Response Plan is Conducted | School Executive | 2026-08-10 | 0 |  | Optional
| School Documents | Review and Comment on Student Code of Conduct | Principal | 2026-08-10 | 0 | Annually | Yes
| Academics | Perform School Testing Year-over-Year Analysis | School Executive | 2026-08-20 | -10 |  | Yes
| Academics | Perform School Testing/EOC Results Database | School Executive | 2026-08-20 | -10 |  | Yes
| Academics | Maintain School Grade/Evaluation History Spreadsheet | School Executive | 2026-09-09 | -30 |  | Yes
| Compliance/Governance | Order Initial Curriculum Large Orders for Semester 2 | School Executive | 2026-10-29 | -80 |  | Yes
| Compliance/Governance | Approve Staffing Plan Submission to Founder | School Executive | 2027-01-22 | -165 |  | Yes
| Human Resources | Prepare for Teacher Evaluations | School Executive | 2027-02-06 | -180 |  | Yes
| Procurement | Plan Y2+ Purchasing (Curriculum, FF&E, Furniture, Supplies, etc.) | School Executive | 2027-02-26 | -200 |  | Yes
| Accounting/Finance | Assist in Audit Procurement | School Executive | 2027-02-26 | -200 |  | Yes
| Compliance/Governance | Founder Approves Principal Evaluation | School Executive | 2027-06-06 | -300 |  | Yes
| Compliance/Governance | Report School Progress: Include Student Achievement Performance Data | School Executive | 2027-08-10 | -365 |  | Yes
| Accounting/Finance | Review Draft of Audited Financials to Ensure in Accordance with School Records: Read the Audited Financial Statement Draft and Provide Comments on the Financial Statements (Including Footnotes) | School Executive | 2027-08-25 | -380 |  | Yes
| Accounting/Finance | Weekly: Enter Journal Entry for Payroll to Track Departments | School Executive | Weekly | Weekly |  | Yes
| Procurement | Weekly: Order Supplies and Other Items As Needed | School Executive | Weekly | Weekly |  | Yes
| Accounting/Finance | Provide Regular Budget to Actual Variance Reports to School Administrators | School Executive | Quarterly | Quarterly |  | Yes
| Accounting/Finance | Quarterly: Run Budget Versus Actual Variance Reports | School Executive | Quarterly | Quarterly |  | Yes
| Accounting/Finance | Monthly: Post Transactions Into the School's General Ledger System on QuickBooks | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Monthly: Maintain Capital Asset Inventory and Track Depreciation | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Monthly: Reconcile, on a Continuous Basis, the Inter-Company Account Balances | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Monthly: Initiate Payments for Benefits | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Monthly: Run Balance Sheet and Note Any Changes to Assets, Liabilities, or Equity | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Maintain Cash Flow Analysis | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Monthly: Reconcile Period Ending Balances and Propose Adjusting Entries in a Manner Consistent with State Standards | School Executive | Monthly | Monthly |  | Yes
| Compliance/Governance | Exercise Continuing Oversight Over School Operations | School Executive | Monthly | Monthly |  | Yes
| Accounting/Finance | Ensure the School Has All Financial Documentation Required for the Annual Audit, as Required by State Statutes | School Executive | Monthly | Monthly |  | Optional
| Accounting/Finance | Daily: Monitor School's Bank Accounts for Activity and Balances | School Executive | Daily | Daily |  | Yes
| Accounting/Finance | Daily: Maintain Clubs/Sports Revenue and Expense Tracking | School Executive | Daily | Daily |  | Yes
| Accounting/Finance | Daily: Provide Timely and Accurate Answers to School Vendors Regarding Payments and Accounts | School Executive | Daily | Daily |  | Yes
| Human Resources | Update all Knowledge Bases | School Executive | As Required | As Required |  | Yes
|  | Manage School Procedures | School Executive | As Required | As Required |  | Yes
|  | Founder handles Parent concerns that rise through the grievance escalation process. | School Executive | As Required | As Required |  | Yes
|  | Founder approves Policy Changes | School Executive | As Required | As Required |  | Yes
| Compliance/Governance | Founder Conducts Internal Investigations & Formal Complaints About Staff | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Maintain Accounting System & Records in Accordance with State Statutes | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Provide AP Aging Report to Approve Bill Pay | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Maintain Accounts Payable & Aging Schedule | School Executive | As Required | As Required |  | Yes
|  | Manage Code of Conduct Changes | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Process Employee Expense Reports | School Executive | As Required | As Required |  | Yes
| Human Resources | Archive Fingerprint Results in Employee/Founder Folders | School Executive | As Required | As Required |  | Yes
| Human Resources | Founder Approves Staff Transfer and Promotion | School Executive | As Required | As Required |  | Yes
| Human Resources | Founder Approves Staff Dismissals | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Enter Payroll Payments Into Accounting System | School Executive | As Required | As Required |  | Yes
| Marketing | Manage School Brochure for Public Relations Image | School Executive | As Required | As Required |  | Yes
| Marketing | Manage School Main Facebook Page for Public Relations Image | School Executive | As Required | As Required |  | Yes
| Marketing | Manage School Profile Edits: To Be to Created and Updated School Profile that a Student Would Send to a College When Applying | School Executive | As Required | As Required |  | Yes
| Marketing | Manage School Third Party Web Pages 1. Google 2. Yelp 3. Niche 4. GreatSchools.com | School Executive | As Required | As Required |  | Yes
| Marketing | Manage Search Engine Optimization (SEO) | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Maintain Vendor Contracts Associated with Expenses and Verify Payments Are Made in Accordance with Specifications in Each Contract | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Negotiate Prices and Terms with Vendors | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Process Rapid Response Vendor Payments | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Process Vendor Payments (At Least Two Times Monthly, Generally Mid-Month and Month end), | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Use Fed Ex Or Other Carrier to Execute Signatures Necessary for Payments Processed Remotely | School Executive | As Required | As Required |  | Yes
| Operations | Maintain Technology Succession Plan | School Executive | As Required | As Required |  | Yes
| Operations | Maintain School Technology Login Credentials | School Executive | As Required | As Required |  | Yes
| Operations | Email System- Mass Email Contact Updates: 1. Add new Employees 2. Add New student families 3. Changes for existing families and Employees 4. Remove Employees as the leave the school 5. Remove families as they leave school 6. Manage accidental "Un-subscribes" monthly | School Executive | As required | As Required |  | Yes
| School Documents | Update Policies on School Website As Required | School Executive | As Required | As Required |  | Optional
| Operations | Recommend technology purchase as required | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | Prepare Payments and Submit for Approval | School Executive | As Required | As Required |  | Yes
| Accounting/Finance | As Required: Create Updates to Budget | School Executive | As Required | As Required |  | Yes
| Compliance/Governance | Fictitious Name Registration Renewal Due in October | School Executive | Annually | Annually |  | Yes
| Facility Management | Annually: Manage Facility Periodic Requirements by Facility Manager | School Executive | Annually | Annually |  | Yes
| School Documents | Annually Maintain: School Policies | School Executive | Annually | Annually |  | Yes
| Administrative | Annually Create and Maintain: Speech Language Pathologist Agreement | School Executive | Annually | Annually |  | If Applicable | If Providing Speech Language Services
| School Documents | Annually Create and Maintain: Parent/Student Handbook Template | School Executive | Annually | Annually |  | Yes
| School Documents | Annually Maintain: Health Service Procedures | School Executive | Annually | Annually |  | Yes
| School Documents | Annually Maintain: Dismissal Policies and Procedures | School Executive | Annually | Annually |  | Yes
| School Documents | Annually Maintain: Biomedical Waste Operating Plan | School Executive | Annually | Annually |  | Yes
| Accounting/Finance | Annually: Prepare Information for "Form 1099" | School Executive | Annually | Annually |  | Yes
| Accounting/Finance | Annually: Prepare the Annual-End Statements of Financial Position | School Executive | Annually | Annually |  | Yes
| Accounting/Finance | Annually: Prepare "Form 1099" | School Executive | Annually | Annually |  | Yes
| Compliance/Governance | Founder Update - Corporate Filing | School Executive | Annually | Annually |  | Yes
| Procurement | Post Intent to Award Contract Announcements on Website for Large Contracts | School Executive | Annually | Annually |  | Optional
| Legal | File State Incorporation Annual Report | School Executive | Annually | Annually |  | Yes
Formulas:
Due Date = D1-[Days Before Opening]

## Principal & SOM Checklist (hidden)
Status | Category | Task | Owner | Due Date | Days Before Opening | Frequency | Florida | Microschool?
| Enrollment | Review and verify Registration Packets (Registrar) | SOM | 2025-12-03 | 250 | Annually |  | Yes
| Human Resources | Setup Portal to Human Resources system | HR | 2026-01-02 | 220 |  |  | Yes
| Coordination | Review Equipment by Room; Provide Suggestions. Use Equipment Requirement spreadsheet | SOM | 2025-07-26 | 380 |  |  | Yes
| Coordination | Review and provide input of Furniture Order List By Room | Principal | 2025-07-26 | 380 |  |  | Yes
| Human Resources | Reach out to Local Colleges for Staff Recruitment | HR | 2026-01-02 | 220 |  |  | Yes
| Revenue Management | Market Student Supply Program | SOM | 2026-01-02 | 220 |  |  | Optional
| Curriculum | Curriculum: Manage School Outyear Curriculum selection: 1. Analyze recommendations 2. Evaluate new, changed, deleted recommendations 3. Decide each grade curriculum list See OptimaEd template | Curriculum Coordinator | 2026-01-02 | 220 |  |  | Yes
| Human Resources | Create Cal-OSHA and OSHA Compliant Safety Handbook | HR | 2026-01-02 | 220 | As Required |  | Yes
| Academic Calendar | Set Teacher Start Date for Academic Calendar | Principal | 2026-01-12 | 210 | Annually |  | Yes
| Academic Calendar | Approve School Academic Calendar submission to Founder | Principal | 2025-08-22 | 353 | Annually |  | Yes
| Coordination | Review Staffing Plan | Principal | 2025-07-26 | 380 | Annually |  | Yes
| Coordination | Review Online Systems Plan and Status | Principal | 2026-01-22 | 200 |  |  | Yes
| Coordination | Review Florida Public Records Request Statutes | Principal | 2026-01-22 | 200 |  |  | Yes
| Uniform | Recommend Dress Code/Uniforms | Principal | 2026-01-22 | 200 |  | 1002.33(17)(h) 1011.78 | Yes
| Purchasing | Obtain contract for Water - New Building Construction | SOM | 2026-01-22 | 200 |  |  | Yes
| Purchasing | Obtain contract for Electric Power - New Building Construction | SOM | 2026-01-22 | 200 |  |  | Yes
| Facility Management | Discuss Classroom setup alternatives (Student backs to doormat) | Principal | 2026-01-22 | 200 |  |  | Yes
| Human Resources | Begin Interviewing Faculty Applicants | Principal | 2026-01-22 | 200 |  |  | Yes
| Curriculum | Approve process to Purchase based on Curriculum. Review list and create plan | Principal | 2026-01-22 | 200 |  |  | Yes
| Coordination | Approve Master Schedule and Teacher assignment | Principal | 2025-08-25 | 350 |  |  | Yes
|  | Review Year 1 Founder Approved Staffing Plan | Principal | 2025-09-29 | 315 |  |  | Yes
| Coordination | Review Year 1 Salary Schedule | Principal | 2026-02-06 | 185 |  |  | Yes
| Uniform | Baseline Dress Code/Uniforms | Principal | 2026-02-11 | 180 |  | 1002.33(17)(h) 1011.78 | Yes
| Before & After Care | Finalize Before and After School Care Program | SOM | 2026-03-13 | 150 |  |  | Yes
| Uniforms | Develop Uniform Dress Code Description and Pictures for website | Principal | 2026-03-13 | 150 |  |  | Yes
| Budget | As required: Provide Input to Budget Process | SOM | 2025-10-14 | 300 | Annually |  | Yes
| Budget | As required: Provide Input to Budget Process | Principal | 2025-10-14 | 300 | Annually |  | Yes
| Uniforms | Develop Uniform Dress Code Description and Pictures for website | SOM | 2026-03-23 | 140 |  | FS 1002.33(17)(h) FS 1011.78 | Yes
| Purchasing | Select Student Planner Design | Principal | 2026-03-31 | 132 |  |  | Yes
| Enrollment | Student Local Tracking Database Configured (Registrar) | SOM | 2026-05-02 | 100 |  |  | Yes
| Enrollment | Setup Registrar to enter Student data into SIS system | SOM | 2026-05-02 | 100 |  |  | Yes
| Curriculum | Select samples of textbooks to review | Principal | 2026-05-02 | 100 |  |  | Yes
| Coordination | Review Lesson Plan System | Principal | 2026-05-02 | 100 |  |  | Yes
| Curriculum | Plan PE Curriculum (Curriculum Coordinator) | Principal | 2026-05-02 | 100 |  |  | Yes
| Human Resources | Interview Non-Faculty applicants | SOM | 2026-05-02 | 100 |  |  | Yes
| Curriculum | Curriculum Specifics Content Update if required; decide which books to cover in sequence: Select 1st Semester Textbooks | Principal | 2026-05-02 | 100 |  |  | Yes
| Administrative Duties | Create Yearbook Program - Recruit Yearbook Manager/Producer | Project Coordinator | 2026-05-02 | 100 | As Required |  | Yes
| Registrar | Configure SIS: Enter all student schedules, bells, and periods in SIS from School SIS or what Enrollment Manager provides. (Yearly maintenance and can be changed at any given time with new hires or ESE services) | Registrar | 2026-05-02 | 100 | As Required |  | Yes
| Coordination | Approve Draft Classroom and Student Supplies to purchase | Principal | 2026-05-02 | 100 |  |  | Yes
| Coordination | Approve Draft Classroom and Student Supplies list | Principal | 2026-05-02 | 100 |  |  | Yes
| Human Resources | Hire Administrative Assistant (starts sooner than others) | Principal | 2026-05-12 | 90 |  |  | Yes
| Administrative Duties | Yearbook - Program Advisor and Coordination with company | Project Coordinator | 2026-05-22 | 80 |  |  | Yes
| Security | Review and approve Crisis Response Plan: Work with Optima Template | SOM | 2026-01-22 | 200 |  |  | Yes
| Human Resources | Plan New Hire Orientation Meeting | SOM | 2026-05-22 | 80 |  |  | Yes
| Purchasing | Order Student Planners (in concert with principal) | SOM | 2026-05-22 | 80 |  |  | Yes
| Purchasing | Issue setup of Utilities Connection and setup Monthly payments: Coordinate with construction company Builder will not be coordinating Internet & cable | SOM | 2026-05-22 | 80 |  |  | Yes
| Human Resources | Hire Security Guard | SOM | 2026-05-22 | 80 |  |  | Yes
| Human Resources | Hire Receptionist | SOM | 2026-05-22 | 80 |  |  | Yes
| Human Resources | Hire Ops Specialists | SOM | 2026-05-22 | 80 |  |  | Yes
| Human Resources | Hire Health & Wellness Coordinator | SOM | 2026-05-22 | 80 |  |  | Yes
| Human Resources | Hire Facility Manager | SOM | 2026-05-22 | 80 |  |  | Yes
| Human Resources | Hire Day Porters | SOM | 2026-05-22 | 80 |  |  | Yes
| Enrollment | Evaluate Registration for ESE needs (SSD Director) | Principal | 2026-05-22 | 80 |  |  | Yes
| Administrative Duties | Standardize Classroom Wall Operatives: Keep distracting clutter to minimum | Dean of Students | 2026-06-01 | 70 | As Required |  | Yes
| Student Progression Plan | Review and Comment on Student Progression Plan | Principal | 2026-02-01 | 190 | Annually |  | Yes
|  | Radon Testing and Reporting | SOM | 2026-06-01 | 70 |  | SOM must report results of Radon Testing http://www.floridahealth.gov/environmental-health/radon/ http://www.floridahealth.gov/environmental-health/radon/mandatory-testing.html http://www.floridahealth.gov/environmental-health/radon/radon-menu.html Obtain the Report from the Construction Company Send report to: HSEC_RadonReports@flhealth.gov https://404.056 Environmental radiation standards and projects; certification of persons performing measurement or mitigation services; mandatory testing; notification on real estate documents; rules (4) MANDATORY TESTING.—All public and private school buildings or school sites housing students in kindergarten through grade 12; all state-owned, state-operated, state-regulated, or state-licensed 24-hour care facilities; and all state-licensed day care centers for children or minors which are located in counties designated within the Department of Business and Professional Regulation’s Florida Radon Protection Map Categories as “Intermediate” or “Elevated Radon Potential” shall be measured to determine the level of indoor radon, using measurement procedures established by the department. Initial measurements shall be conducted in 20 percent of the habitable first floor spaces within any of the regulated buildings and shall be completed and reported to the department within 1 year after the date the building is opened for occupancy or within 1 year after license approval for the entity residing in the existing building. Follow-up testing must be completed in 5 percent of the habitable first floor spaces within any of the regulated buildings after the building has been occupied for 5 years, and results must be reported to the department by the first day of the 6th year of occupancy. After radon measurements have been made twice, regulated buildings need not undergo further testing unless significant structural changes occur. No funds collected pursuant to s. http://www.leg.state.fl.us/statutes/index.cfm?App_mode=Display_Statute&Search_String=&URL=0500-0599/0553/Sections/0553.721.html shall be used to carry out the provisions of this subsection. | Yes
| Discipline | Publish Bullying Policy per Policy | Dean of Students | 2026-06-01 | 70 |  |  | Yes
| Administrative Duties | Plan and Implement Literacy Boot Camp for new K-3 students: 1. Add to calendar 2. Create signup form 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event | Dean of Students | 2026-06-01 | 70 |  |  | Yes
| Administrative Duties | Plan and Implement Kindergarten Round Up: 1. Add to calendar 2. Create signup form 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event | Dean of Students | 2026-06-01 | 70 |  |  | Yes
| Curriculum | Perform Textbook Inventory (Curriculum Coordinator). Must create delivery packages per classroom. | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Yearbook and Pictures | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Visitor Management System | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Trash Removal | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Security Monitoring | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Recycle Removal | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Landscaping (Lawn, Bushes, Blowing & Fertilizing) | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Fire Sprinkler System Inspection | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Fire Alarm Monitoring | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for ESE Speech Consultant | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for ESE Psychologist Consultant | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Custodian Service | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Car Line System | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain contract for Pest Control company | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Obtain agreement of Supply Company for Dispensers for new building only? | SOM | 2026-06-01 | 70 |  |  | Yes
| Revenue Management | Market Classroom Supply Program | SOM | 2026-06-01 | 70 |  |  | Yes
| Coordination | Initiate Lesson Plan development by teachers as they are hired | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Spanish Teachers | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Physical Education Teachers: K-6 Certified | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Music Teachers | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Latin Teacher | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire K-6 Teachers | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Exceptional Education Director | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire ESE Teachers | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Assistant Principal | Principal | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Hire Art Teachers | Principal | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Find handyman for minor work at school | SOM | 2026-06-01 | 70 |  |  | Yes
| Administrative Duties | Ensure that Student Progression Plan is uploaded to website | SOM | 2026-02-01 | 190 |  |  | Yes
| Security | Ensure that All vendors are checked against Jessica Lunsford Act | SOM | 2026-06-01 | 70 |  |  | Yes
| Discipline | Discuss Bullying Policy per Policy at an assembly | Dean of Students | 2026-06-01 | 70 |  |  | Yes
| Revenue Management | Develop Reading Plan | Principal | 2026-06-01 | 70 | Annually |  | Yes
| Human Resources | Decide if we Post Qualification of Teachers on their web pages? Ask principal; Headhunters can target them | SOM | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Create Website accounts for New staff | SOM | 2026-06-01 | 70 |  |  | Yes
| Security | Create Threat Assessment Team | SOM | 2026-06-01 | 70 |  | FS 1006.07 (6) (c) Annually (c)?Each district school board and charter school governing board must adopt an active assailant response plan. By October 1, 2019, and annually thereafter, each district school superintendent and charter school principal shall certify that all school personnel have received annual training on the procedures contained in the active assailant response plan for the applicable school district or charter school. | Yes
| Discipline | Create and Publish Behavioral Expectations per Policy | Dean of Students | 2026-06-01 | 70 |  |  | Yes
| Sports | Create and market after school Sports. Approval of Principal for Teacher participation | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Window Cleaning | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Water/Sewer | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Sign Repairs | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Roof Repairs & Maintenance (R&M) | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Pressure Cleaning Building, Sidewalk and Signage | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Plumbing R&M | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Parking Lot Lighting R&M | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Mold Testing | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Lock and Key | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Landscape Fertilizing | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Fire Sprinkler System R&M | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Fire Extinguisher Annual Inspection | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Fire Alarm System R&M Service | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Fire Alarm System Annual Certification | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Exterior Lighting Maintenance | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Elevator R&M | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Elevator Preventive Maintenance and R&M (can wait) | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Elevator License | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Elevator Annual Inspection | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Electrical R&M | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Copy Machines Lease | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Building Exterior R&M (can wait) | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with Asphalt R&M (can wait) | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Contract with A/C Service Contract and R&M | SOM | 2026-06-01 | 70 |  |  | Yes
| Human Resources | Confirm Teachers Certification is on track | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Approve Draft Office and Facility Supplies to purchase | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Approve Draft Office and Facility Supplies list | SOM | 2026-06-01 | 70 |  |  | Yes
| Curriculum | Accept Textbook Delivery (Curriculum Coordinator): Must inventory and sign Invoice for payment | SOM | 2026-06-01 | 70 |  |  | Yes
| Purchasing | Accept Supplies Deliveries. Need to create delivery packages per classroom. Must inventory and sign Invoice for payment | SOM | 2026-06-01 | 70 |  |  | Yes
| Curriculum | Complete a Textbook Inventory | SOM | 2026-06-11 | 60 |  |  | Yes
| Code of Student Conduct | Review and Comment on Student Code of Conduct | Principal | 2026-03-13 | 150 | Annually |  | Yes
| Human Resources | Review, Edit and Approve Student Remediation Strategy | Principal | 2026-06-21 | 50 |  | Florida Class Size Amendment | Yes
| Human Resources | Work with IT to create school folders for Departments and Staff if applicable | SOM | 2026-07-11 | 30 |  |  | Yes
| Human Resources | Work with IT to add New staff to files/Drive | SOM | 2026-07-11 | 30 |  |  | Yes
| Human Resources | Work with IT on creating email accounts for New Staff | SOM | 2026-07-11 | 30 |  |  | Yes
| Enrollment | Update Student Database with registrations (Registrar) | SOM | 2026-07-11 | 30 | Annually |  | Yes
| Human Resources | Start-Up Services (complete service to set up new school Overhead) | HR | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Wi-Fi system | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Security | Setup and Configure Visitor screening Application | Visitor Security System Consultant | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Switches | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| State Testing | Setup and Configure State Testing Laptops | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Staff Microsoft Office | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Staff G-Suite Email system | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Staff Computers - UPS | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Staff Computers - Laptops | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Staff Computers - iPads | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Staff Computers - Desktops | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Servers | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Security: Virus Protection | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Security: Patching Process | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Security: Password Policies | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Security: Internal Security | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Public Address System | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Office Fax/Monochrome Printers | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Office Color Printers | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Office Check Printers | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Internet Access | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Hardware Server (Authentication, Print Server, etc.) | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure G-Suite Users | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure G-Suite Data Storage | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Facility Management | Setup and Configure Copiers | Facility Manager | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Classroom Projectors | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Car Line Sound System | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Cameras -Hallway | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Cameras - Server software | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Cameras - External | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Camera - Hardware | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure Cafeteria Projector | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Setup and Configure VOIP phone System | Technology Vendor | 2026-07-11 | 30 | As Required |  | Yes
| Administrative Duties | Review Biomedical Waste Operating Plan for Clinic. See Optima Template for plan | SOM | 2026-07-11 | 30 |  |  | Yes
| Enrollment | Request Student Records (Registrar) | SOM | 2026-07-11 | 30 |  |  | Yes
| Purchasing | Receive and Sign for Furniture Delivery and Installation Must inventory and sign invoice for payment | SOM | 2026-07-11 | 30 |  |  | Yes
| Coordination | Receive and Sign for Equipment | SOM | 2026-07-11 | 30 |  |  | Yes
| Administrative Duties | Post prominently the contact information for the agency's custodian of public records in the in front Lobby | SOM | 2026-07-11 | 30 |  | FS 119.12 (2) | Yes
| Discipline | Post Notice stating that a student's locker or other storage area is subject to search | SOM | 2026-07-11 | 30 |  | FS 1006.09(9) (9)?A school principal or a school employee designated by the principal, if she or he has reasonable suspicion that a prohibited or illegally possessed substance or object is contained within a students locker or other storage area, may search the locker or storage area. The district school board shall require and each school principal shall cause to be posted in each public K-12 school, in a place readily seen by students, a notice stating that a students locker or other storage area is subject to search, upon reasonable suspicion, for prohibited or illegally possessed substances or objects. | Yes
| Curriculum | Post Curriculum: Update Map on school website per Policy | Curriculum Coordinator | 2026-07-11 | 30 |  |  | Yes
| Administrative Duties | Place Child Abuse Poster in school | SOM | 2026-07-11 | 30 |  | FS 1006.061(4)(a) | Yes
| Facility Management | Obtain Health Certificate | SOM | 2026-07-11 | 30 |  |  | Yes
| Facility Management | Obtain Fire Inspection. Keep for records. | SOM | 2026-07-11 | 30 |  |  | Yes
| Facility Management | Obtain Facility Health Inspection from County Health. Keep for records | SOM | 2026-07-11 | 30 |  |  | Yes
| Security | Obtain contract for Staff Badges. Will help teachers get discounts | SOM | 2026-07-11 | 30 |  |  | Yes
| Administrative Duties | Obtain Certificate of Occupancy from Builder | SOM | 2026-07-11 | 30 |  |  | Yes
| Building Construction | Obtain Asbestos Inspection and Certificate from builder | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Install VOIP System | SOM | 2026-07-11 | 30 |  |  | Yes
| Security | Install Visitor control system | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Install Switches | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Install Servers | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Install Security Cameras | SOM | 2026-07-11 | 30 |  |  | Yes
| Facility Management | Install protective slides on all desks and/or chairs to protect floors | Facility Manager | 2026-07-11 | 30 | As Required |  | Yes
| Technology | Install PA System | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Install Networking Technology | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Install Internet Router | SOM | 2026-07-11 | 30 |  |  | Yes
| Human Resources | Hire two Recess Monitors 8 hours a day (could be stay at home parents) | Principal | 2026-07-11 | 30 |  |  | Yes
| Human Resources | Hire seven K-6 Instructional Assistants 8 hours a day (could be stay at home parents) | Principal | 2026-07-11 | 30 |  |  | Yes
| Human Resources | Hire Physical Education Assistants 4 hours a day (could be stay at home parents) | Principal | 2026-07-11 | 30 |  |  | Yes
| Building Construction | Finalize Asbestos Management Plan | SOM | 2026-07-11 | 30 |  |  | Yes
| Administrative Duties | Develop Day One Procedures | SOM | 2026-07-11 | 30 |  |  | Yes
| State Testing | Designate a testing coordinator for proper state test administration | SOM | 2026-07-11 | 30 |  |  | Yes
| Security | Create Student Badge? | SOM | 2026-07-11 | 30 |  |  | Yes
| Purchasing | Contract with ESE Consultants | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Configure staff computers | SOM | 2026-07-11 | 30 |  |  | Yes
| Security | Complete FSSAT | SOM | 2026-07-11 | 30 |  |  | Yes
| Building Construction | Assign a Staff to serve as the School Asbestos Coordinator per Policy. Ensure he/she is trained. | SOM | 2026-07-11 | 30 |  |  | Yes
| Transportation | Approve Bus routes by July 30 per Policy | SOM | 2026-07-11 | 30 |  |  | Yes
| Technology | Accept and sign for Technology Delivery | SOM | 2026-07-11 | 30 |  |  | Yes
| Kindergarten Roundup | Support Kindergarten Roundup | SOM | 2026-07-21 | 20 |  |  | Yes
| Human Resources | Staff are Fingerprinted and cleared | HR | 2026-07-21 | 20 |  |  | Yes
| Coordination | Decide on IXL use for Math remediation: Each student has an account. Could have a after school club. | Principal | 2026-07-21 | 20 |  |  | Yes
| Kindergarten Roundup | Review and Approve Kindergarten Roundup Plan: Just prior to start of school to decide which kids to separate. | Principal | 2026-07-26 | 15 |  |  | Yes
| Kindergarten Roundup | Conduct Kindergarten Roundup (just prior to start of school to decide which kids to separate) | Principal | 2026-07-27 | 14 |  |  | Yes
| Training | Start Teacher Orientation | Principal | 2026-07-31 | 10 |  |  | Yes
| Administrative Duties | Setup Employment Posters on bulletin boards | Project Coordinator | 2026-07-31 | 10 | As Required |  | Yes
| Improvement Plan | Reporting progress toward meeting the school's goals and objectives to the Founder | Principal | 2026-07-31 | 10 |  | FS 1002.33(9)(k) | Yes
| Enrollment | Receive Student Records (Registrar) | SOM | 2026-07-31 | 10 |  |  | Yes
| State Testing | Prepare and Test Technology for State Pre-Test | Project Coordinator | 2026-07-31 | 10 |  |  | Yes
| Administrative Duties | Post required Human Resources notices in Teacher workrooms 1. Employee Rights under the Fair Labor Standards Act 2. Job Safety and Health: It&#x27;s the Law 3. Employee Rights and Responsibilities Under The Family and Medical Leave Act 4. Pay Transparency Nondiscrimination Provision (41 CFR Part 60-1.3 | Project Coordinator | 2026-07-31 | 10 | As Required |  | Yes
| Physical Education | Plan to have Certified PE instructor review PE curricula and programs | Principal | 2026-07-31 | 10 |  | FS 1003.455 | Yes
| Parent Notification | Notify parents of PE Opt-Out options | Curriculum Coordinator | 2026-07-31 | 10 |  | FS 1003.455 | Yes
| Facility Management | Install Room/Teacher Signage | SOM | 2026-07-31 | 10 |  |  | Yes
| Administrative Duties | Install Clocks in classrooms (if required) | SOM | 2026-07-31 | 10 |  |  | Yes
| Facility Management | If leasing - Rekey all doors | SOM | 2026-07-31 | 10 |  |  | Yes
| Curriculum | Have Certified PE instructor review PE curricula and programs | Curriculum Coordinator | 2026-07-31 | 10 |  | FS 1003.455 | Yes
| Enrollment | Enter Student Data Into SIS system (Registrar) | SOM | 2026-07-31 | 10 |  |  | Yes
| Facility Management | Display of the state motto, "In God We Trust," in front lobby | SOM | 2026-07-31 | 10 |  | FS 1003.44 | Yes
| Security | Create Team for Early Warning System | Principal | 2026-07-31 | 10 |  | FS 1001.42 (18)(b) | Yes
| Clubs | Create and market after school clubs | SOM | 2026-07-31 | 10 | As Required |  | Yes
| State Testing | Create and Maintain Detail State Test Technology Plan | Project Coordinator | 2026-07-31 | 10 |  |  | Yes
| Students | Manage Locker/Cubby Assignments 1. Assign by Homeroom and Gender 2. Update as required 3. Provide assignment lists to staff | SOM | 2026-07-31 | 10 |  |  | Yes
| Administrative Duties | Teachers Prepare Classrooms | Principal | 2026-08-07 | 3 |  |  | Yes
| Enrollment | Conduct Open House for parents | Principal | 2026-08-07 | 3 |  |  | Yes
| Enrollment | Conduct Open House | Principal | 2026-08-07 | 3 |  |  | Yes
| Kindergarten Roundup | Conduct Kindergarten Roundup (just prior to start of school to decide which kids to separate?) | SOM | 2026-08-08 | 2 |  |  | Yes
| Administrative Duties | Plan and Implement Kindergarten Open House 1. Add to calendar 2. Prepare Student Class sheets 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event Principal provides direction | Project Coordinator | 2026-08-08 | 2 |  |  | Yes
| Training | Conduct Initial Before School Staff Training | Principal | 2026-08-09 | 1 | Annually |  | Yes
Formulas:
Due Date = 'Detailed Checklist'!D$1-[Days Before Opening]

## NSLP (hidden)
Status | Category | Task | Notes | Owner | Due Date | Days Before Opening | Frequency | Florida
NSLP | Food Service | SAM registration annual renewal date is 1/8/21 |  | SOM | 2025-08-10
NSLP | Meal Program | Explicitly plan for lunch period | Work with principal to plan | SOM | 2025-08-10
NSLP | Meal Program | Get 2 Food Managers Certified | Review with CMO | SOM | 2025-08-10
NSLP | Meal Program | Free and Reduced Meal Applications Updated Online Ordering System |  | SOM | 2025-08-10 |  | As Required
NSLP | Meal Program | 1. School Wellness Policy Team - Develop team | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10 |  | Annually
NSLP | Meal Program | 1. School Wellness Policy Team - Meet annually (at least one time per year) | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10 |  | Annually
NSLP | Meal Program | 1. School Wellness Policy Team - Send updated copy to the Florida Department of Agriculture and Consumer Services (FDACS) when a change or revision is made. | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 1. School Wellness Policy Team - Ensure compliance with federal and state regulations for competitive food and beverage items sold on the school campus (7 CFR 210.11 and FAC 5P-1.003); | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 1. School Wellness Policy Team - Maintain a school calendar identifying the dates when exempted competitive food fundraisers will occur in accordance with the frequency specified in paragraph (c) of FAC 5P-2.002; | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 1. School Wellness Policy Team - Report school’s compliance of the regulations to the school principal/school operations manager | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 1. School Wellness Policy Team - Assess wellness policy at least every three years following the triennial assessment | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 2. School Wellness Policy - Nutrition Promotion | Refer to latest version of policy for details Review and consider evidence-based strategies and techniques in establishing goals for nutrition promotion and education, physical activity and other school-based activities that promote student wellness to include, at a minimum, a review of Smarter Lunchroom tools and techniques. | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 3. School Wellness Policy - Nutrition Education (Regularly 2019/Quarterly 2020) | Refer to latest version of policy for details Students receive quarterly nutrition education that is interactive and teaches skills they need to adopt healthy eating behaviors. Classroom lectures, activities and student participation are provided in nutrition and health classes. | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 3. School Wellness Policy - Nutrition Education (Annually) | Refer to latest version of policy for details The staff responsible for health/nutrition education will be adequately prepared and participate at least annually in professional development activities to effectively deliver an accurate nutrition education program as planned. Preparation and professional development activities will provide basic knowledge of nutrition combined with skill practice in program-specific activities and instructional techniques and strategies designed to promote healthy eating habits. | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 4. School Wellness Policy - Physical Activity | Refer to latest version of policy for details Ensure required PE requirements are scheduled accordingly | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 5. School Wellness Policy - Other School-Based Activities | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 6. School Wellness Policy - Follow Guidelines for All F&B Available During the School Day | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 7. School Wellness Policy - Follow Policy for F&B Marketing | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 8. School Wellness Policy - Evaluation and Measurement of the Implementation of the Wellness Policy | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10 |  | Annually
NSLP | Meal Program | 9. School Wellness Policy - Informing the Public | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 10. School Wellness Policy - Community Involvement | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
NSLP | Meal Program | 11. School Wellness Policy - Record Keeping | Refer to latest version of policy for details | Health & Wellness Coordinator | 2025-08-10
| NSLP | Monthly: Review and issue employee reimbursements |  |  | Monthly | Monthly |  |  | Charter | Private | 1
| NSLP | Monthly: Utilize school website to review form revenue and request disbursements |  |  | Monthly | Monthly |  |  | Charter | Private | 1

## Principal Checklist (hidden)
Charter School Principal Checklist
Status | Category | Task | Notes | Owner/Third Party | Item
|  | Decide on IXL use for Math remediation | Decide on IXL use for Math remediation Each student has an account. Could have a after school club. | Principal
| Human Resources | Review, Edit and Approve Remediation Strategy | Affects Staffing & CSA: Review with Chuck | Principal
| Administrative Duties | Progress monitoring | Progress monitoring 1. FAIR 2. DIBELS 4. Math assessments 5. Other assessments as needed | Dean of Students
| College | Conduct PSAT Recruitment program | Future Years | College Advisor
| College | Conduct PSAT at School | Future Years | College Advisor
| College | Conduct PSAT Admin Test preparation | Future Years | College Advisor
| College | Take PSAT training to learn how to access and use scores | Future Years | College Advisor
| College | Researching additional methods for CLT, ACT and SAT test preparation | Future Years | College Advisor
| College | Manage school Classical Learning Test (CLT) Account | Future Years | College Advisor
| College | Plan and manage School CLT Test in Fall | Future Years | College Advisor
| College | Plan and manage School CLT Pre-Test in Fall | Future Years | College Advisor
| Administrative Duties | Standardize Classroom Wall Operatives |  | Dean of Students
| Administrative Duties | Plan and Implement Literacy Boot Camp for new K-3 students | Plan and Implement Riggs Boot Camp for new K-3 students 1. Add to calendar 2. Create signup form 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event After first year | Dean of Students
| Administrative Duties | Plan and Implement Kindergarten Round Up | Plan and Implement Kindergarten Round Up 1. Add to calendar 2. Create signup form 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event | Dean of Students
| Purchasing | Select Student Planner Design |  | Principal
| Academic Calendar | Establish First Day of School for second year |  | Principal
| Enrollment | Conduct Open House for parents |  | Principal
| Enrollment | Conduct Open House | Planned and coordinated by SOM for principal | Principal
| Administrative Duties | Teachers Prepare Classrooms |  | Principal
| Kindergarten Roundup | Conduct Kindergarten Roundup (just prior to start of school to decide which kids to separate?) |  | Principal
| Kindergarten Roundup | Develop Kindergarten Roundup Plan | (just prior to start of school to decide which kids to separate?) Need to plan | Principal
| Human Resources | Review, Edit and Approve Use of Supplements |  | Principal
|  | Review Year 1 Salary Schedule |  | Principal | Salary Schedule Planning Year
|  | Review Salary Schedule |  | Principal | Salary Schedule Annual
| Budget | As required: Provide Input to Budget Process |  | Principal | Budget
|  | Review and Approve Club Sponsor plan and $1,000 supplement |  | Principal
|  | Review and Approve Sports Sponsor plan and $500 Assistant Coach supplement |  | Principal
|  | Review and Approve Sports Sponsor plan and $2,000 Head Coach supplement |  | Principal
| Administrative Duties | Parent Communications |  | Dean of Students
| Administrative Duties | Communicate with parents with monthly Principal's Perspective email |  | Principal
| Administrative Duties | Principal's Perspective email? Do you want one? When to start? |  | Principal
| Parent Notification | Archive Survey period Items for possible Audit: | Rule: 6A-1.0503 (3) Archive Survey period Items for possible Audit: - SE IEPs and EPs, including Program Eligibility documentation | Student Services Director
| ESE Program | Psychological Services Information submission |  | Student Services Director
| Administrative Duties | Manage Third Grade Retention Process |  | Student Services Director
| Administrative Duties | Annually notify parents of any K-3rd grade student who exhibits a substantial deficiency in reading, that retention is possible. | Post list to website | Student Services Director
| Discipline | Create and Publish Behavioral Expectations per Policy 4.3.4 |  | Dean of Students
| Discipline | Publish Bullying Policy per Policy 4.3.9.14h |  | Dean of Students
| Discipline | Discuss Bullying Policy per Policy 2300 at an assembly |  | Dean of Students
| Security | Guidance Counseling: Track Mental Health Assistance Usage | 1011.62(16)(d) | Guidance Counselor | Mental Health
| Code of Student Conduct | Discuss Code of Student Conduct at beginning of year in every class. - Principal/SOM | FS 1006.07(2) Annually | Teachers | CoC
| Improvement Plan | Reporting progress toward meeting the school's goals and objectives to the Board | FS 1002.33(9)(k) | Principal
| Security | Guidance Counseling: Manage Mental Health Assistance Plan | 1011.62(16)(d) | Guidance Counselor | Mental Health
| Administrative Duties | As Required: Attend board meetings and present relevant or requested information |  | Principal
| Policies | Approve Grading per grade level in Policy (could change) |  | Principal
| Parent Notification | Notify parents of PE Opt-Out options per FS1003.455 | FS 1003.455 | Curriculum Coordinator
| College | Create and Manage 8th Grade Academic Plans | Future Years | College Advisor
| Evaluations | Approves Class Roster Teacher assignments for February Survey. (This is for VAM impact preparation.) | FS 1012.34 (1)(a) Is not required if we do not use VAM for Teacher growth scores. | Principal
|  | Confirm that all teachers review and Confirm Class Rosters are correct in PowerSchool | This is especially true for Specialty Teachers. | Principal
|  | Approve School Academic Calendar submission to Board |  | Principal
|  | Set Teacher Start Date for Academic Calendar |  | Principal
| Enrollment | Principal or SOM and Registrar Attend Sponsor Training |  | Principal | Training
| Security | Create Team for Early Warning System | FS 1001.42 (18)(b) | Principal
| Security | Register with FortifyFL mobile reporting application; Work with the Sponsor School Safety Specialist | Well need to add your school to the app database first. Please contact me over the summer and we can add your school, link it to local law enforcement responders and identify who will get notified in the event of any tips for your school. Julie Collins Email: FortifyFL@fldoe.org Office of Safe Schools 850-245-0676 | Principal
| Academic Calendar | Set Teacher Start Date for Academic Calendar |  | Principal
|  | Send FERPA Email to parents in newsletter as a link to website notice PDF | 34 CFR 99.7 | Principal | FERPA
|  | Approve Class Roster Teacher assignments for February Survey | Approves Class Roster Teacher assignments for February Survey. (This is for VAM impact preparation.) | Principal
| Security | Principal sends Active Assailant Training Certification to SafeSchools@fldoe.org . | FS 1006.07(6)(c) | Principal
| Revenue Management | Review Reading Plan Legislation Updates with Chuck | Legislation has changed what charter schools do. | Principal
| Academic Calendar | Approve School Academic Calendar submission to Board |  | Principal
| Student Progression Plan | Review and Comment on Student Progression Plan |  | Principal | SPP
| Code of Student Conduct | Review and Comment on Student Code of Conduct |  | Principal | CoC
|  | Review Florida Public Records Request Statutes |  | Principal
| Training | Plan and Conduct Monthly School Improvement Training sessions for faculty |  | Principal
| Certification | In lieu of college credit or the equivalent inservice specified in subparagraph (3)(b)1. of this rule, the charter school chief administrator shall provide a statement certifying to extenuating circumstances beyond the control of the teacher to earn such credit during the prescribed time | Rule: 6A-1.0503 (4) Annually | Principal
| Administrative Duties | Plan the school instructional program |  | Principal
| Administrative Duties | Verify Reports Cards for accuracy |  | Principal
| Administrative Duties | Maintain familiarity with Charter School Florida Statutes, Rules and Technical Advisory Notices. |  | Principal
|  | Review class rosters for February Survey | FS 1012.34 (1)(a) Provide instructional personnel the opportunity to review their class rosters for accuracy and to correct any mistakes for February Survey. (This is for VAM impact preparation.) | Principal
|  | Sign and send home February Out-of-Field Teacher Letters | 1012.42?Teacher teaching out-of-field.(1)?ASSISTANCE.Each district school board shall adopt and implement a plan to assist any teacher teaching out-of-field, and priority consideration in professional development activities shall be given to a teacher who is teaching out-of-field. The district school board shall require that the teacher participate in a certification or staff development program designed to provide the teacher with the competencies required for the assigned duties. The board-approved assistance plan must include duties of administrative personnel and other instructional personnel to provide students with instructional services. | Principal | OOF
|  | Approve February Out-of-Field Teacher List | Rule: 6A-1.0503 (3) Annually | Principal | OOF
|  | Sign and send home Out-of-Field Teacher Letters | FS 1012.42 | Principal | OOF
|  | Approve October Out-of-Field Teacher List | Rule: 6A-1.0503 (3) Annually | Principal | OOF
|  | Approve Semester 1 Out-of-Field Teacher List | Board approves out of field teacher list Paper or electronic notice to parents of students in teachers&#x27; classes Post list to website Archive board approved minutes of meeting with list approval FS 1012.42 1012.42?Teacher teaching out-of-field.(1)?ASSISTANCE.Each district school board shall adopt and implement a plan to assist any teacher teaching out-of-field, and priority consideration in professional development activities shall be given to a teacher who is teaching out-of-field. The district school board shall require that the teacher participate in a certification or staff development program designed to provide the teacher with the competencies required for the assigned duties. The board-approved assistance plan must include duties of administrative personnel and other instructional personnel to provide students with instructional services. (2)?NOTIFICATION REQUIREMENTS.When a teacher in a district school system is assigned teaching duties in a class dealing with subject matter that is outside the field in which the teacher is certified, outside the field that was the applicants minor field of study, or outside the field in which the applicant has demonstrated sufficient subject area expertise, as determined by district school board policy in the subject area to be taught, the parents of all students in the class shall be notified in writing of such assignment, and each school district shall report out-of-field teachers on the districts website within 30 days before the beginning of each semester. A parent whose student is assigned an out-of-field teacher may request that his or her child be transferred to an in-field classroom teacher within the school and grade in which the student is currently enrolled. The school district must approve or deny the parents request and transfer the student to a different classroom teacher within a reasonable period of time, not to exceed 2 weeks, if an in-field teacher for that course or grade level is employed by the school and the transfer does not violate maximum class size pursuant to s. 1003.03 and s. 1, Art. IX of the State Constitution. If a request for transfer is denied, the school must notify the parent and specify the reasons for the denial. An explanation of the transfer process must be made available in the student handbook or a similar publication. This subsection does not provide a parent the right to choose a specific teacher | Principal | OOF
| Training | SESIR Training | https://www.flrules.org/gateway/RuleNo.asp?ID=6A-1.0017 (10) Training required. Each district superintendent must designate persons responsible for SESIR reporting in the district and ensure that all such persons receive the on-line training found at http://sesir.org. SESIR training provided by Department staff can be used to satisfy the online training requirement. (11) Accountability for SESIR reporting. In order to enhance SESIR reporting, the persons or entity listed below have the following responsibilities: (a) School principals. Each public school principal, including charter school principals or equivalent, must ensure that all persons at the school responsible for SESIR information participate in the training set forth in subsection (10) of this rule and must ensure that SESIR data is accurately and timely reported. Training can be found at: http://www.sesir.org/Home.aspx/Index | Principal
|  | Principal reviews draft Mental Health Allocation Plan with Sponsor Rep |  | Principal | Mental Health
| College | Handle Course code questions/ choosing | Future Years | College Advisor
| Compliance | Maintain School Chemical Management Plan | Future Years | Chemistry Classroom Teacher
| Compliance | Maintain School Chemical Inventory | Future Years | Chemistry Classroom Teacher
| Evaluations | Provide instructional personnel the opportunity to review their class rosters for accuracy and to correct any mistakes for February Survey. (This is for VAM impact preparation.) | FS 1012.34 (1)(a) | Principal
| IXL | IXL: Manage IXL Membership Accounts | IXL: Manage IXL Membership Accounts 1. Add new staff and students as required 2. Delete old staff and students as required 3. Pull Reports for Principal as required | Dean of Students
| IXL | IXL: Administer the IXL program as the Admin |  | Dean of Students
| Discipline | Create Model lessons for teachers |  | Dean of Students
| Administrative Duties | Propose new course applications as required by FDOE |  | Dean of Students
| Administrative Duties | Implement the planned school instructional program |  | Principal
| Administrative Duties | Evaluate the planned school instructional program |  | Principal
| Administrative Duties | Review Course Syllabi's |  | Dean of Students
| Administrative Duties | Multiplication Math Fact Progress Monitoring |  | Dean of Students
| Administrative Duties | Execute DIBEL test 3 TIMES A YEAR |  | Dean of Students
| Purchasing | Supplies: Manage Math Manipulatives selection | Supplies: Manage Math Manipulatives selection 1. Standardize 2. Identify needs by type 3. Identify need by Grade 4. Identify need by Upper School Course 5. Calculate numbers needed by quarter 6. Create order list and submit to Business Manager who will confirm budget compliance See Chuck for template Quarterly | Curriculum Coordinator
| Curriculum | Curriculum: Manage School Curriculum procurement | Curriculum: Manage School Curriculum procurement 1. Determine number of books per grade and subject 2. Obtain Principal approval on order 3. Submit order to Business Manager, for confirmation of budget compliance 4. Track curriculum inventory for informing next year purchase see chuck for template | Curriculum Coordinator | Curriculum Ordering
| Curriculum | Curriculum: Mentor teachers on use of Curriculum |  | Curriculum Coordinator | Curriculum
|  | Review Online Systems Plan and Status | See spreadsheet. | Principal
| Curriculum | Have Certified PE instructor review PE curricula and programs IAW 1003.455 | FS 1003.455 | Curriculum Coordinator
| Physical Education | Plan PE classes for Kindergarten, 1st, 2nd, 3rd, 4th, 5th and 6th grade |  | Elementary PE Teacher
| Curriculum | Curriculum: Manage School Outyear Curriculum selection | Curriculum: Manage School Outyear Curriculum selection 1. Analyze Hillsdale recommendations (annual spreadsheet) 2. Evaluate new, changed, deleted recommendations 3. Decide each grade curriculum list see chuck for template | Curriculum Coordinator | Curriculum Ordering
| Curriculum | Post Curriculum: Update Map on school website per Policy 5.1.2 |  | Curriculum Coordinator | Curriculum
| Curriculum | Order initial Curriculum from small providers (Amazon, etc.) for semester 2 |  | Curriculum Coordinator | Curriculum Ordering
|  | Review and provide input of Furniture Order List By Room |  | Principal | Furniture
| Physical Education | Plan to have Certified PE instructor review PE curricula and programs IAW 1003.455 | FS 1003.455 | Principal
| Curriculum | Purchase initial Curriculum Amazon Orders (Curriculum Coordinator) |  | Principal | Curriculum Ordering
| Curriculum | Plan PE Curriculum (Curriculum Coordinator?) |  | Principal | Curriculum
| Curriculum | Curriculum Specifics Content Update if required; decide which books to cover in sequence | Select 1st Semester Textbooks? | Principal | Curriculum Ordering
| Curriculum | Select samples of textbooks to review? |  | Principal
| Curriculum | Curriculum Specifics Content Review |  | Principal | Curriculum Ordering
| Curriculum | Approve process to Purchase | Review list and create plan | Principal | Curriculum Ordering
| Curriculum | Review Curriculum selection process |  | Principal | Curriculum Ordering
| Discipline | Review Security Video for investigations |  | Dean of Students
| Discipline | Manage Elementary School recurring discipline issues with Guidance techniques |  | Guidance Counselor
| Discipline | Conduct In-School Detention |  | Dean of Students
| Discipline | Elementary School Discipline Management |  | Dean of Students
| Grievance Process | Handles Parent concerns that rise through the grievance escalation process. |  | Principal
|  | Send Enrollment Team a List of Retained Students | The Enrollment Team will use this information to adjust the number of Open Seats in SchoolMint using the following example formulae for 1st Grade: Next Year’s Open Seats for 1st Grade = Planned Total students for 1st Grade – Current Kindergarten students + Not Returning Kindergarten Students + Retained Kindergarten Students - Retained 1st grade students Our Back Office Operations Specialists currently send us the students that have announced that they are not returning and we update the open seats as we receive them. | Principal
|  | Review current Enrollment status and alternatives |  | Principal | Enrollment
| Evaluations | Prepare for Teacher Evaluations | FS 1012.34 Prepare for Teacher Evaluations 1. Watch FCPCS Video | Principal
| Evaluations | Review Evaluation System Requirements (2 evals in first year) |  | Principal | FCPCS
| Evaluations | Meet with each faculty member and review/sign "Summative Evaluation Rating (SER)" form | FS 1012.34 | Principal
| Evaluations | Perform required faculty Evaluations (2 x in first year of employment) | FS 1012.34 | Principal
| Evaluations | Perform required Amin Evaluations (Assistant Principal/Dean of Students) | FS 1012.34 | Principal
| Extra Curricular | Sponsor for National Honor Society Club |  | Classroom Teacher
| Extra Curricular | Sponsor 5th Grade Geo Bee |  | Classroom Teacher
| Extra Curricular | Sponsor 3rd Grade Spelling Bee |  | Classroom Teacher
| Extra Curricular | Sponsor 5th Grade Spelling Bee |  | Classroom Teacher
| Extra Curricular | Sponsor for House System Development |  | Classroom Teacher
| Extra Curricular | Sponsor for Mu Alpha Theta Club |  | Classroom Teacher
| Extra Curricular | Sponsor for National Junior Classical League |  | Classroom Teacher
| Extra Curricular | Sponsor for Scholar Bowl Team |  | Classroom Teacher
| Extra Curricular | Sponsor Julius Caesar (Parent production) |  | Classroom Teacher
| Extra Curricular | Sponsor 10th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 11th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 12th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 2nd Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 2nd Grade Poetry Recitation |  | Classroom Teacher
| Extra Curricular | Sponsor 3rd Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 3rd Grade Scripps National Spelling Bee |  | Classroom Teacher
| Extra Curricular | Sponsor 4th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 5-12 Talent Show |  | Classroom Teacher
| Extra Curricular | Sponsor 5th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 6th Grade Blue and Gold Semiformal |  | Classroom Teacher
| Extra Curricular | Sponsor 5th Grade Music Showcase |  | Classroom Teacher
| Extra Curricular | Sponsor 8th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 6th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 7th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor 9th Grade Movie Night |  | Classroom Teacher
| Extra Curricular | Sponsor After-School Activities Fair |  | Classroom Teacher
| Extra Curricular | Sponsor An Evening of Art |  | Classroom Teacher
| Extra Curricular | Sponsor Chorus and Symphonia Concert |  | Classroom Teacher
| Extra Curricular | Sponsor K-4 Talent Show |  | Classroom Teacher
| Extra Curricular | Sponsor Kindergarten Showcase |  | Classroom Teacher
| Administrative Duties | Assist Principal in Planning events (staff meetings, assemblies, Student Appreciation Night, etc.) | Assist Principal in Planning events (staff meetings, assemblies, Student Appreciation Night, etc.) 1. Identify upcoming events 2. Identify needs of the event 3. Reach out to those involved | Dean of Students
|  | Review School Event Planning options; see calendar of possibilities |  | Principal
| Administrative Duties | Review teacher lesson plans and instruction |  | Principal
|  | Initiate Lesson Plan development by teachers as they are hired |  | Principal
|  | Review Lesson Plan System |  | Principal
| ESE Program | Submit ESE MIP training to Registrar |  | Student Services Director
| Administrative Duties | Assist Teachers in Enrichment and Remediation |  | Instructional Assistant
| Training | Conduct Teacher Training |  | Hillsdale | Hillsdale
| Administrative Duties | Provide Teacher Training Support | Provide Teacher Training Support 1. Provide curriculum for teacher Training 2. Provide general pacing guidelines for teacher training 3. Create schedules for teacher training 4. Create graphs and charts for teacher training 5. Create lesson plans for teacher training | Dean of Students
| Training | Staff start First Year | All Teachers as well | Principal | Hillsdale Training
| Training | Plan and Conduct Beginning of Year Orientation Training for staff |  | Principal
| Administrative Duties | Mentor teachers as required |  | Principal
| Training | Staff Complete | All Teachers as well | Principal | Hillsdale Training
| Training | Conduct Teacher Orientation |  | Principal
| Training | Plan Teacher Orientation (and MIPS Tracking) |  | Principal
| Training | Staff Complete First Year Teacher Training | All Teachers as well | Principal | Hillsdale Training
| Training | Complete Teacher Orientation |  | Principal
| Training | Start Teacher Orientation |  | Principal
| Scheduling | Track and plan new and returning Elementary School student schedules | May change responsibility | Guidance Counselor
| Scheduling | Create Next Year's Elementary School Course Schedule | May change responsibility | Guidance Counselor
| Scheduling | Elementary Student Assignments to Course Schedule | May change responsibility | Guidance Counselor
| Administrative Duties | Confirm that all courses are covering required Florida state standards for each grade |  | Dean of Students
|  | Approve Master Schedule and Teacher assignment |  | Principal
| Scheduling | Create Initial Daily Schedule final | Will be used in Student data System setup | Principal
| Scheduling | Review, Edit and Approve Class Scheduling |  | Principal
| Purchasing | Supplies: Manage School Science Supplies selection | Supplies: Manage School Science Supplies selection 1. Standardize 2. Identify needs by type 3. Identify need by Grade 4. Identify need by Upper School Course 5. Calculate numbers needed by quarter 6. Create order list and submit to Business Manager who will confirm budget compliance Quarterly | Curriculum Coordinator
| Purchasing | Supplies: Manage School Classroom Supplies selection | Supplies: Manage School Classroom Supplies selection 1. Standardize 2. Identify needs by type 3. Identify need by Grade 4. Identify need by Upper School Course 5. Calculate numbers needed by quarter 6. Create order list and submit order, for confirmation of budget compliance See Chuck for template Quarterly | Curriculum Coordinator
| Revenue Management | Review and Approve - Student Supply Program |  | Principal
|  | Approve Draft Classroom and Student Supplies list |  | Principal | Supplies
|  | Approve Draft Classroom and Student Supplies to purchase |  | Principal | Supplies
| ESE Program | Manage Speech Pathologist |  | Student Services Director
| ESE Program | Manage ESE Process and IEP Meetings |  | Student Services Director
| ESOL | ESOL: CELLA testing in the beginning of the year. |  | Guidance Counselor
| ESOL | Review Home Language Survey |  | Guidance Counselor
| ESOL | ESOL: Test ELL in first days of school year. |  | Guidance Counselor
| ESOL | Notify parents of ESOL placement |  | Guidance Counselor
| ESOL | ESOL: Ensure paperwork is complete for ELL compliance | Attend trainings (2 a semester) | Guidance Counselor
| ESOL | ESOL: Attend ELL meetings |  | Guidance Counselor
| ESOL | ESOL: WIDA testing in January-February |  | Guidance Counselor
| Enrollment | Evaluate Registration for ESE needs (SSD Director) |  | Principal
| ESE Program | Oversee IEP process |  | Principal
| Human Resources | Interview New Faculty as required |  | Principal
| Human Resources | Review, Edit and Approve Classroom Assistant Staffing |  | Principal
|  | Review Staffing Plan |  | Principal | Staffing Plan Annual
| Human Resources | Begin Interviewing Faculty Applicants |  | Principal
|  | Review role of Dean of Students |  | Principal
| Security | Review role of Guidance Counselor (Mental Health Allocation Plan) |  | Principal | Mental Health
|  | Review marketing role (Calendar, Substitute Program, Field trips, Social events, FAST Testing) |  | Principal
|  | Review role of Non-Medical Assistants (Guidance Counselor, Receptionist, Registrar) |  | Principal
|  | Review role of Compliance Manager |  | Principal
|  | Review Year 1 Staffing Plan |  | Principal | Staffing Plan Planning Year
| Administrative Duties | Assign duties to Classroom Assistants |  | Principal
| Human Resources | Hire two Recess Monitors 8 hours a day (could be stay at home parents) |  | Principal
| Human Resources | Hire Physical Education Assistants 4 hours a day (could be stay at home parents) | Could be full time, but what else would they do?? | Principal
| Human Resources | Hire seven K-6 Instructional Assistants 8 hours a day (could be stay at home parents) |  | Principal
| Human Resources | Hire Spanish Teachers | Spanish Certified | Principal
| Human Resources | Hire Physical Education Teachers | K-6 Certified | Principal
| Human Resources | Hire Music Teachers | Music Certified | Principal
| Human Resources | Hire Latin Teacher | Latin Certified | Principal
| Human Resources | Hire K-6 Teachers | K-6 Certified | Principal
| Human Resources | Hire Exceptional Education Director | K-6 Certified | Principal
| Human Resources | Hire ESE Teachers | K-6 Certified | Principal
| Human Resources | Hire Assistant Principal | K-6 Certified would be preferred | Principal
| Human Resources | Hire Art Teachers | Art Certifed | Principal
| Human Resources | Hire Administrative Assistant (starts sooner than others) |  | Principal
| Curriculum | Hire Curriculum Coordinator | K-6 Certified | Principal | Curriculum
| Human Resources | Review, Edit and Approve Recess Monitoring Staffing |  | Principal
| Human Resources | Review, Edit and Approve PE Assistant Staffing |  | Principal
| Curriculum | Review role of Curriculum Coordinator/Dean of CI |  | Principal | Curriculum Ordering
| Extra Curricular | Sponsor High School Prom |  | Classroom Teacher
| Uniform | Recommend Dress Code/Uniforms | 1002.33(17)(h) 1011.78 | Principal
| Uniform | Baseline Dress Code/Uniforms | 1002.33(17)(h) 1011.78 | Principal
| Uniforms | Develop Uniform Dress Code Description and Pictures for website |  | Principal
| Extra Curricular | Sponsor National Latin Exam (7-12) |  | Classroom Teacher
| Extra Curricular | Sponsor National Junior Classical League Game Nights - grades 6-12 |  | Classroom Teacher
| Scheduling | FLVS -Monitor and Approve HS Students Courses |  | Upper School Dean
| Scheduling | Send Final FLVS Grade reports to Registrar when student completes course |  | Upper School Dean
| Seniors | Manage National Honor Society account |  | Upper School Dean
| Seniors | Manage Senior Transcript Creation Process |  | Upper School Dean
| Seniors | Oversee Next Year Student Graduation Status | Track status of EEI (Algebra 1 EOC, 24 Credits, GPA, etc.) | Upper School Dean
| Grades | Manage Student Grade Adjustment based on 30% EOC impact | Algebra 1, Biology | Upper School Dean
| Sports | Filling out and ensuring compliance with FHSAA. |  | Elementary PE Teacher
| Sports | Coaching sports teams (supplement) |  | Elementary PE Teacher
| Sports | Athletic Fundraisers |  | Elementary PE Teacher
| Administrative Duties | Manage Morning Car Line | Manage Morning Car Line 1. Directing Traffic 2. Umbrellas if needed 3. Additional mats if rain May change responsibility | Guidance Counselor
| Students | Manage Locker/Cubby Assignments | Manage Locker/Cubby Assignments 1. Assign by Homeroom and Gender 2. Update as required 3. Provide assignment lists to staff | Upper School Dean
| College | Scholarship Research | Future Years | College Advisor
| College | Create next year Upper school class schedule | Future Years | College Advisor
| Discipline | Upper School Discipline Management |  | Dean of Students
| Seniors | Managing Rqts for high school graduation so that all seniors graduate | Future Years | College Advisor
| College | Create Upper school class scheduling Template | Future Years | College Advisor
| College | Create and Maintain College Handbook Template | Future Years | College Advisor
| College | Track and plan new and returning Upper School student schedules | Future Years | College Advisor
| College | Perform Next Year Course Scheduling for each student in Upper School | Future Years | College Advisor
| College | Manage HS Student Interviews of incoming High School students | Future Years | College Advisor
| College | Working with AP and other schools to get our AP scores from last year sent to us | Future Years | College Advisor
| College | Create "Senior Spotlight" writeups | Future Years; For each Senior; to be posted on Website | College Advisor
| College | Manage New High School Student Credit Transfer Process | Future Years | College Advisor
| College | Manage 8th grade Math planning for current 7th graders | Future Years | College Advisor
| College | Researching careers for students based on interests stated in their meetings (necessary criteria to get that career)� | Future Years | College Advisor
| College | Recommend scholarship opportunities | Future Years | College Advisor
| College | Reading over student essays for scholarships to give them feedback | Future Years | College Advisor
| College | Prepare scholarship materials to pass out to students in homerooms | Future Years | College Advisor
| College | Prepare for College Fair | Future Years | College Advisor
| College | Post and updating scholarships on school bulletin boards | Future Years | College Advisor
| College | Meet with Students on College planning | Future Years | College Advisor
| College | Manage School College Board account | Future Years Manage School College Board account 1. AP 2. SAT/SAT 3. Access Manager | College Advisor
| College | Customize College Handbook | Future Years | College Advisor
| College | Conduct Homeroom College briefings | Future Years | College Advisor
| College | Assorted College Advising - PSAT training | Future Years | College Advisor
Purchasing
Administrative Duties
Administrative Duties
Human Resources
Facility Management
| Curriculum |  |  |  | Curriculum Ordering
| Curriculum |  |  |  | Curriculum Ordering
Curriculum
Certification
Human Resources
Kindergarten Roundup
Kindergarten Roundup
Uniforms
| Curriculum |  |  |  | Curriculum Ordering
| Curriculum |  |  |  | Curriculum
| Curriculum |  |  |  | Curriculum
| Curriculum |  |  |  | Curriculum
| Curriculum |  |  |  | Curriculum
| Curriculum |  |  |  | Curriculum
| Curriculum |  |  |  | Curriculum
| Curriculum |  |  |  | Curriculum
College
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Before & After Care
| Budget |  |  |  | Budget
Building Construction
Building Construction
Building Construction
Clubs
Clubs
Clubs
Clubs
Clubs
Clubs
Clubs
Clubs
Discipline
| Enrollment |  |  |  | Training
| Enrollment |  |  |  | Training
Enrollment
| Enrollment |  |  |  | Enrollment
Enrollment
| Enrollment |  |  |  | Enrollment
Enrollment
Enrollment
Enrollment
Enrollment
Enrollment
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
| FLKRS |  |  |  | FLKR
| FLKRS |  |  |  | FLKR
Food Service
FSA Testing
FSA Testing
FSA Testing
Grievance Process
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Human Resources
Inventory
Inventory
Meal Program
Meal Program
Meal Program
Parent Notification
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
| Purchasing |  |  |  | Supplies
| Purchasing |  |  |  | Supplies
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
| Purchasing |  |  |  | Supplies
| Purchasing |  |  |  | Furniture
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Revenue Management
Revenue Management
Revenue Management
Revenue Management
Revenue Management
Security
Security
Security
Security
Security
Security
Security
Security
Security
Security
Security
Security
Sports
Students
| Technology |  |  |  | Technology
| Technology |  |  |  | Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Training
Transportation
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
Custodial
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Employee Insurance |  |  |  | ESI: Insurance
| Employee Insurance |  |  |  | ESI: Insurance
| Employee Insurance |  |  |  | ESI
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Employee Insurance |  |  |  | esi
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Policies |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
| Human Resources |  |  |  | ESI
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Facility Management
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Meal Program
Administrative Duties
Administrative Duties
| FLKRS |  |  |  | FLKR
Administrative Duties
Administrative Duties
Administrative Duties
| FLKRS |  |  |  | FLKR
| FLKRS |  |  |  | FLKR
FSA Testing
FSA Testing
Administrative Duties
FSA Testing
| Technology |  |  |  | Technology
FSA Testing
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Administrative Duties
Clubs
FSA Testing
Purchasing
Purchasing
Purchasing
Purchasing
Purchasing
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Receptionist
Registrar
| FLKRS |  |  |  | FLKR
Parent Notification
Parent Notification
Parent Notification
Parent Notification
| Registrar |  |  |  | Enrollment
| Registrar |  |  |  | Enrollment
| Registrar |  |  |  | Enrollment
Reporting
Discipline
| Registrar |  |  |  | Enrollment
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Registrar
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Technology
Security

## Operations Checklist (hidden)
Charter School Operations Leader Checklist
Status | Category | Task | Notes
Approve Copy Machines Requirements
Review Copy Machine Requirements
|  | Assist with Events | Assist with Events 1. Teacher workshops 2. Writers Workshop 3. Fundamentals of Mathematics 4. Literature lesson training
School Safety
|  | Review, Edit and Approve Room Assignments | Review with Optima
Discuss Classroom setup alternatives (Student backs to door; Phones on wall near door)
|  | Accept Textbook Delivery (Curriculum Coordinator) | Must inventory and sign Invoice for payment
|  | Perform Textbook Inventory (Curriculum Coordinator). Must create delivery packages per classroom. | Must inventory and sign Invoice for payment
|  | Complete a Textbook Inventory | See Chuck/Principal for tracking SS.
Confirm Teachers Certification is on track
|  | Do Not Post Qualification of Teachers on their web pages? | Ask principal; Headhunters can target them.
|  | Kindergarten Roundup (support principal) | Review with principal
|  | Conduct Kindergarten Roundup (just prior to start of school to decide which kids to separate?) | Review with Principal
|  | Develop Uniform Dress Code Description and Pictures for website | FS 1002.33(17)(h) FS 1011.78
|  | Approve Ordering curriculum materials | Approve Ordering curriculum materials using 1. Hillsdale Bill of Materials 2. Principals requests 3. Teacher requests 4. Identify quantity needs
|  | Curriculum 1: Manage Outyear curriculum books | Curriculum 1: Manage Outyear curriculum books 1. Planning book purchases 2. Counting 3. Keeping logbook updated 4. Delivering 5. Collecting
|  | Curriculum 5: End of Year Process - Book collection | Curriculum 5: End of Year Process - Book collection 1. Collecting books as they are completed during the year 2. Counting returned books and logging in the log book 3. Check books for damage 4. Book repair and notation 5. Notifying Purchasing of damage replacement 6. Put books away in stock room
|  | Curriculum 2: Summer assistance | Curriculum 2: Summer assistance 1. Inventory Books 2. Receiving books 3. Stamp books 4. Deliver books to classroom
|  | Curriculum 6: Delivery as required | Curriculum 6: Delivery as required 1. Deliver materials 2. Collect materials 3. Receiving new materials and processing 4. Notify Purchasing of needs
|  | Curriculum 3: Print/bind additional Curriculum resources. | Curriculum 3: Print/bind additional Curriculum resources. 1. Make Core Knowledge binders 2. Make Comb-bound of various texts (observing copyright limits) 3. Pearson Education 4. Beacon readers 5. Grammar books
|  | Curriculum 4: Managing Lost/Damaged books | Curriculum 4: Managing Lost/Damaged books 1. Cost to teacher 2. Follow up with Receptionist regarding payment 3. Put books away
|  | Curriculum 7: Manage Book Storage Room | Curriculum 7: Manage Book Storage Room 1. Putting away books 2. Stamping books 3. Repairing damaged books 4. Label and tidy shelves
|  | Assist College Advisor | With any paperwork they need for student who are applying to Colleges or volunteering opportunities.
|  | Ensure that Student Progression Plan is uploaded to website | Annually
Send Teacher Certification List to Sponsor
Submit Fire Inspection to Sponsor
Submit Health Inspection to Sponsor
Develop Day One Procedures
|  | Post prominently the contact information for the agency's custodian of public records in the in front Lobby | FS 119.12 (2)
Obtain Certificate of Occupancy from Builder
|  | Review Biomedical Waste Operating Plan | See Chuck for plan
|  | Send List of Teachers to Sponsor | Can we do this via Focus?
Post Records request Notice in Front Lobby per 119.12
|  | Place Child Abuse Poster in school | FS 1006.061(4)(a)
Ensure that Non Medical Assistants (NMA) receive Training
Install Clocks in classrooms (if required)
Manage Parent Facebook Group as Admin
Recess Monitor - Requesting replacement supplies from Purchasing
Manage School Website for Public Relations Image
Manage IT Services Firm
Customize Parent/Student Handbook
|  | Manage Student Parking Program | Manage Student Parking Program 1. Purchase permits on-line during summer 2. Annually market program over summer 3. Conduct Student Parking lottery if required 4. Issue Permits See chuck for template
|  | Finalize Before and After School Care Program | Unless we staff it our selves
As required: Provide Input to Budget Process
Assign a Staff to serve as the School Asbestos Coordinator per Policy 8.4.2. Ensure he/she is trained.
Obtain Asbestos Inspection and Certificate from builder
Finalize Asbestos Management Plan
|  | Create and market after school clubs | Approval of Principal for Teacher participation
Recruit Faculty Sponsor for House System Development
Recruit Faculty Sponsor for Mu Alpha Theta Club
Recruit Faculty Sponsor for National Honor Society Club
Recruit Faculty Sponsor for National Junior Classical League
Recruit Faculty Sponsor for Scholar Bowl Team
Support Latin Teachers in Planning and Conducting National Mythology Exam
Support Latin Teachers in Planning and Conducting the National Latin Exam
|  | Notice stating that a student's locker or other storage area is subject to search | FS 1006.09(9) (9)?A school principal or a school employee designated by the principal, if she or he has reasonable suspicion that a prohibited or illegally possessed substance or object is contained within a students locker or other storage area, may search the locker or storage area. The district school board shall require and each school principal shall cause to be posted in each public K-12 school, in a place readily seen by students, a notice stating that a students locker or other storage area is subject to search, upon reasonable suspicion, for prohibited or illegally possessed substances or objects.
Principal or SOM and Registrar Attend Sponsor Training
Registrar Attends Sponsor Training
Review/Validate Registration Packets (Registrar)
Review and verify Registration Packets (Registrar)
Request Student Records (Registrar)
Update Student Database with registrations (Registrar)
Enter Student Data Into Sponsor system (Registrar)
Receive Student Records (Registrar)
Setup Registrar to enter Student data into Sponsor system
Student Local Tracking Database Configured (Registrar)
|  | Radon Testing and Reporting | SOM must report results of Radon Testing http://www.floridahealth.gov/environmental-health/radon/ http://www.floridahealth.gov/environmental-health/radon/mandatory-testing.html http://www.floridahealth.gov/environmental-health/radon/radon-menu.html Obtain the Report from the Construction Company Send report to: HSEC_RadonReports@flhealth.gov https://404.056 Environmental radiation standards and projects; certification of persons performing measurement or mitigation services; mandatory testing; notification on real estate documents; rules (4) MANDATORY TESTING.—All public and private school buildings or school sites housing students in kindergarten through grade 12; all state-owned, state-operated, state-regulated, or state-licensed 24-hour care facilities; and all state-licensed day care centers for children or minors which are located in counties designated within the Department of Business and Professional Regulation’s Florida Radon Protection Map Categories as “Intermediate” or “Elevated Radon Potential” shall be measured to determine the level of indoor radon, using measurement procedures established by the department. Initial measurements shall be conducted in 20 percent of the habitable first floor spaces within any of the regulated buildings and shall be completed and reported to the department within 1 year after the date the building is opened for occupancy or within 1 year after license approval for the entity residing in the existing building. Followup testing must be completed in 5 percent of the habitable first floor spaces within any of the regulated buildings after the building has been occupied for 5 years, and results must be reported to the department by the first day of the 6th year of occupancy. After radon measurements have been made twice, regulated buildings need not undergo further testing unless significant structural changes occur. No funds collected pursuant to s. http://www.leg.state.fl.us/statutes/index.cfm?App_mode=Display_Statute&Search_String=&URL=0500-0599/0553/Sections/0553.721.html shall be used to carry out the provisions of this subsection.
|  | Radon Testing and Reporting - 5th Year | SOM must report results of Radon Testing http://www.floridahealth.gov/environmental-health/radon/ http://www.floridahealth.gov/environmental-health/radon/mandatory-testing.html http://www.floridahealth.gov/environmental-health/radon/radon-menu.html Obtain the Report from the Construction Company Send report to: HSEC_RadonReports@flhealth.gov https://404.056 Environmental radiation standards and projects; certification of persons performing measurement or mitigation services; mandatory testing; notification on real estate documents; rules (4) MANDATORY TESTING.—All public and private school buildings or school sites housing students in kindergarten through grade 12; all state-owned, state-operated, state-regulated, or state-licensed 24-hour care facilities; and all state-licensed day care centers for children or minors which are located in counties designated within the Department of Business and Professional Regulation’s Florida Radon Protection Map Categories as “Intermediate” or “Elevated Radon Potential” shall be measured to determine the level of indoor radon, using measurement procedures established by the department. Initial measurements shall be conducted in 20 percent of the habitable first floor spaces within any of the regulated buildings and shall be completed and reported to the department within 1 year after the date the building is opened for occupancy or within 1 year after license approval for the entity residing in the existing building. Followup testing must be completed in 5 percent of the habitable first floor spaces within any of the regulated buildings after the building has been occupied for 5 years, and results must be reported to the department by the first day of the 6th year of occupancy. After radon measurements have been made twice, regulated buildings need not undergo further testing unless significant structural changes occur. No funds collected pursuant to s. http://www.leg.state.fl.us/statutes/index.cfm?App_mode=Display_Statute&Search_String=&URL=0500-0599/0553/Sections/0553.721.html shall be used to carry out the provisions of this subsection.
|  | Kindergarten Boo Hoo Breakfast | Review with principal; Get parent Volunteer to coordinate
Obtain Health Certificate
Obtain Facility Health Inspection from County Health. Keep for records
Obtain Fire Inspection. Keep for records.
If leasing - Rekey all doors
Install Room/Teacher Signage
|  | Display of the state motto, "In God We Trust," in front lobby | FS 1003.44
Obtain FLKR Login
Prepare for and conduct FLKR test (get login account)
SAM registration annual renewal date is 1/8/21
|  | Provide adequate technological infrastructure | Collier 2.B.6 Annually The School shall, at its expense, provide adequate technological infrastructure to support all required online test administration.
|  | Designate a testing coordinator for proper test administration | Collier 2.B.4 Annually The School shall designate a testing coordinator and shall be responsible for proper test administration.
|  | Post Link to Sponsor Uniform Calendar on School Assessment Webpage | FS 1008.22 (7)(d)
SOM Handle Parent concerns that rise through the grievance escalation process.
Hire Registrar (soon as possible)
Interview Non-Faculty applicants
Plan New Hire Orientation Meeting
Hire Receptionist
Hire Ops Specialists
Hire Health & Wellness Coordinator
Hire Facility Manager
Hire Day Porters
Hire Security Guard
Create Website accounts for New staff
Work with IT to create school folders for Departments and Staff if applicable
Work with IT on creating email accounts for New Staff
Work with IT to add New staff to files/Drive
Ensure Staff complete SafeSchools training
Ensure Staff complete DCF training
Manage Staff Responsibility Matrix
Manage Org Chart as required
Interview New Admin Staff as required
Remove Ex-Employees from Website Account System
Remove Ex-Employees from SIS System
Remove Ex-Employees from Email System
Enroll New Employee in Website Account System
Enroll New Employee in Student SIS System
Enroll New Employee in Email System
Train new volunteers
Process Employee Expense Reports
|  | Ensure items are properly inventoried | Must inventory for payment
Manage Property Inventory process
|  | Explicitly plan for lunch period | Work with principal to plan
Get 2 Food Managers Certified
Free and Reduced Meal Applications Updated Online Ordering System
Review Year 1 Salary Schedule
Initial meeting between Optima and SOM
Review Marketing Role
Review role of Non-Medical Assistants (Guidance Counselor, Receptionist, Registrar)
Review Responsibilities of Operations Staff
Review Service Company Requirements
Review Salary Schedule
|  | Review Equipment by Room; Provide Suggestions | Use NCA Equipment Requirement spreadsheet
|  | Receive and Sign for Equipment | Use NCA Equipment Requirement spreadsheet
|  | Preparing for Survey period Items for possible Audit: | Rule: 6A-1.0503 (3) &#x27;- Statement from school leader, on school letterhead that every student reported for funding was in attendance at least one day during the Oct and Feb Survey attendance window (provide dates) and that the attendance maintained on the students is accurate.
|  | Contract with ESE Consultants | Based on principal&#x27;s approval
|  | Issue setup of Utilities Connection and setup Monthly payments | Coordinate with construction company Builder will not be coordinating Internet & cable
Order Student Planners (in concert with principal)
Obtain contract for Electric Power - New Building Construction
Obtain contract for Water - New Building Construction?
Obtain contract for Pest Control company
Obtain contract for Custodian Service
Obtain contract for Yearbook and Pictures
Obtain contract for Fire Alarm Monitoring
Obtain contract for Fire Sprinkler System Inspection
Obtain contract for Landscaping (Lawn, Bushes, Blowing & Fertilizing)
Obtain contract for Recycle Removal
Obtain contract for Security Monitoring
Obtain contract for Trash Removal
Obtain agreement of Supply Company for Dispensers for new building only?
Obtain contract for Car Line System
Find Bus service companies for Field Trips.
Find handyman for minor work at school
Approve Draft Office and Facility Supplies to purchase
Approve Draft Office and Facility Supplies list
Contract with Roof Repairs & Maintenance (R&M)
Contract with Water/Sewer
Obtain contract for ESE Speech Consultant
Obtain contract for ESE Psychologist Consultant
Obtain contract for Visitor Management System
|  | Accept Supplies Deliveries. Need to create delivery packages per classroom. | Must inventory and sign Invoice for payment
|  | Receive and Sign for Furniture Delivery and Installation | Must inventory and sign invoice for payment
Contract with Copy Machines Lease
Contract with Landscape Fertilizing
Contract with A/C Service Contract and R&M
Contract with Asphalt R&M (can wait)
Contract with Building Exterior R&M (can wait)
Contract with Electrical R&M
Contract with Elevator Annual Inspection
Contract with Elevator License
Contract with Elevator Preventive Maintenance and R&M (can wait)
Contract with Elevator R&M
Contract with Exterior Lighting Maintenance
Contract with Fire Alarm System Annual Certification
Contract with Fire Alarm System R&M Service
Contract with Fire Extinguisher Annual Inspection
Contract with Fire Sprinkler System R&M
Contract with Lock and Key
Contract with Mold Testing
Contract with Parking Lot Lighting R&M
Contract with Plumbing R&M
Contract with Pressure Cleaning Building, Sidewalk and Signage
Contract with Sign Repairs
Contract with Window Cleaning
Daily: Print, scan, file all supporting documentation for purchases and payments
Initiate payment for goods and services after verifying receipt of product or service
|  | Daily: Provide Approval on large purchases | May require 2 signatures
Daily: Approve Purchase requests
Match purchase orders to invoices before payment
Process Purchase Order requests
Market Classroom Supply Program
Market Student Supply Program
Daily: Collect all cash received reports from employees and track revenue
Manage Cash
Weekly: Prepare and deposit funds in Bank
Ensure that All vendors are checked against Jessica Lunsford Act
|  | Register with FortifyFL mobile reporting application; Work with the Sponsor School Safety Specialist | Well need to add your school to the app database first. Please contact me over the summer and we can add your school, link it to local law enforcement responders and identify who will get notified in the event of any tips for your school. Julie Collins Email: FortifyFL@fldoe.org Office of Safe Schools 850-245-0676
|  | Review and approve Crisis Response Plan | Work with Optima
Create Threat Assessment Team per Policy 6.4.5.
|  | Create Threat Assessment Team | FS 1006.07 (6) (c) Annually (c)?Each district school board and charter school governing board must adopt an active assailant response plan. By October 1, 2019, and annually thereafter, each district school superintendent and charter school principal shall certify that all school personnel have received annual training on the procedures contained in the active assailant response plan for the applicable school district or charter school.
Complete FSSAT
Install Visitor control system
|  | Obtain contract for Staff Badges | Will help teachers get discounts
Create Student Badge?
|  | Update Active Assailant Response Plan, if required | Annually FS 1006.07 (6)(c)?Each district school board and charter school governing board must adopt an active assailant response plan. By October 1, 2019, and annually thereafter, each district school superintendent and charter school principal shall certify that all school personnel have received annual training on the procedures contained in the active assailant response plan for the applicable school district or charter school.
SOM/Sponsor Trains Staff on Active Assailant Plan
Manage Application: Visitor Screening
|  | Create and market after school Sports | Approval of Principal for Teacher participation
|  | Manage Locker/Cubby Assignments | Manage Locker/Cubby Assignments 1. Assign by Homeroom and Gender 2. Update as required 3. Provide assignment lists to staff
Install Networking Technology
|  | Accept and sign for Technology Delivery | Need receiving location
Install Switches
Install Servers
Install Security Cameras
Install Internet Router
Install VOIP System
Install PA System
Configure staff computers
|  | SESIR Training | https://www.flrules.org/gateway/RuleNo.asp?ID=6A-1.0017 (10) Training required. Each district superintendent must designate persons responsible for SESIR reporting in the district and ensure that all such persons receive the on-line training found at http://sesir.org. SESIR training provided by Department staff can be used to satisfy the online training requirement. (11) Accountability for SESIR reporting. In order to enhance SESIR reporting, the persons or entity listed below have the following responsibilities: (a) School principals. Each public school principal, including charter school principals or equivalent, must ensure that all persons at the school responsible for SESIR information participate in the training set forth in subsection (10) of this rule and must ensure that SESIR data is accurately and timely reported. Training can be found at: http://www.sesir.org/Home.aspx/Index
Approve Bus routes by July 30 per Policy 5800
|  | Clean Building after school hours, per contract | see chuck for template
Break down boxes and move to recycle or garbage- daily.
Clean and Restock Restrooms Before and After Events
Clean Cafeteria Doors daily in AM
Clean Classroom Desks daily with anti-septic
Clean Classroom Floors that custodial service missed - report
Clean Teacher Cafe daily
|  | Clean Teacher Workroom daily | Clean Teacher Workroom daily 1. Clean work table 2. Clean kitchen area 3. Clean out the refrigerator weekly (Friday)
Clean staff coffee pots and prep for next day
Clean Staff Refrigerators weekly
Clean up Cafeteria after special events
Clean up Kitchen after special events as necessary
|  | Clean windows | Clean windows 1. Front lobby and tidy the area 2. Back recess doors 3. Other recess doors
Clean/Polish piano
|  | Coffee and tea station | Coffee and tea station 1. Refilling supplies 2. Brewing coffee as needed 3. Notifying Purchasing when to reorder
|  | Keep top of Lockers/Cubbies clean | Keep top of Lockers/Cubbies clean 1. Books in cubbies 2. Clean off trash
Remove classroom Trash daily that custodial service missed
Restock Boys and Men's restrooms
Restock K Classroom, Girls, Family and Women's Restrooms
Tidy Teacher workrooms daily
Vacuum teacher workroom weekly or more often if needed
Refill staff coffee station supplies
Set up food for special events as necessary
|  | Copiers: Manage Copy Rooms daily | Copiers: Manage Copy Rooms daily 1. Tidy copy rooms 2. Re-supply copy rooms 3. Make copies for the teachers as needed 4. Restock paper in copy machines as required 5. Replace Toner and staples as required
Start-Up Services (complete service to set up new school Overhead)
Produce labor to sales reports
Integrate all payroll expenses to the general ledger
Daily: Per Employee requests, create 401k and/or HSA deduction changes
|  | HR Maintains Certification Data Elements | Staff SSN Staff Sponsor ID Staff Position assignments Teacher College Degree Teacher assignments (ESOL/ESE/Gifted) Teacher FDOE# Teacher Highly Qualified Status Teacher Certification Subject Teacher Certification Issue date Teacher Certification Expiration date Teacher Endorsements Teacher Certification status Teacher Certification level Teacher In-Field/Out-of-Field/Eligible Status Teacher passed the appropriate subject area test in the subject area assigned? Teacher holds a valid infield Professional Certificate in the area assigned. Teacher has a major in the subject area assigned Teacher has equivalent courses in the subject area assigned Teacher has a passing score on the subject area exam in the subject area assigned as evidenced by a valid infield certificate.
Act as liaison between client, employees, brokers and insurance carriers
Audit all insurance bills on a monthly basis to ensure accuracy
Notify management of employees who become eligible for insurance on a monthly basis
Provide employee census information to insurance agents for annual enrollment
Review enrollment forms for accuracy and submit to insurance carrier
Daily: Per Employee requests, submit benefit changes to Medical Insurance provider
Track court-mandated child insurance benefits, notify employee and work to enroll employee and child(ren) on company insurance if/when eligible
Unemployment Insurance and claim litigation
Enroll New Employee in Medical Insurance
Provide Employment Practices Liability Insurance (EPLI)
|  | Appeal all EDD Notices of Unemployment Insurance Claims Filed in an effort to keep the client's unemployment rate low | Note* Appeal to Florida Department of Economic Opportunity
Process Workers Compensation Liability Insurance Certificate requests
Track Staff completion of SafeSchool Training
Maintains Status of mandatory Training. Submits to Compliance Manager for submittal to Sponsor
Advises faculty of required processes for training and certifications
Track Staff completion of DCF Training
|  | Specialized Training | HR, FLSA, Benefits, Portals etc. Not teacher training
|  | Direct Deposit or manual payroll check | ESI is 100% paperless but we offer Direct Deposit or Cash Card (Reloadable virtual bank account)
Social Security Number (SSN) Verification Report
Send New Employee Offer Letters as required
Release of Information Consent Form
Process New Employee Contract Completion
Process New Employee Application Submissions
Family Medical Leave Act (FMLA) Administration
Enroll New Employee in Retirement Program
Employment Verification
EEOC Charge Facilitation
EEO-1 Report
Conduct Fair Labor Standards Act (FLSA) Review
Workers' Compensation and Risk Management
General Human Resources Assistance
General Compliance Assistance
Benefit Management, Bill Reconciliation
|  | Thank You Letter to Applicants Not Selected | Would need to discuss this further to make sure we are on the same page
|  | Employment Records | No performance related docs unless provided by the school
|  | Set Up, Review and Maintain Employee Personnel Files | From a compliance perspective, not performance
|  | New Hire Orientation Program | ESI provides all New Hire Paperwork via secured portal including Employment Agreement, W-4, I-9, Direct Deposit, Benefits Enrollment forms, Handbook, and more.
Track vacation, sick leave and/or personal leave accruals
Provide monthly reports for owner/management regarding: Terminations
Provide monthly reports for owner/management regarding: Other reports as requested
Provide monthly reports for owner/management regarding: New hires
Provide monthly reports for owner/management regarding: I-9 Audit Reports
Provide monthly reports for owner/management regarding: Benefits eligibility
Consult with management prior to disciplinary action and/or termination
Consult with designated personnel on any management issues
Attend meetings with managers and employees or groups of employees to deal with work-related problems affecting performance
Assist management in actual handling of disciplinary action and/or termination
Answer questions for employees on vacation accruals, benefits, etc.
|  | Provide monthly reports for owner/management regarding: Current salaries | We can provide scheduled, monthly reports to designated staff, as well as provide same day reporting on-demand.
|  | Provide unlimited access to human resources forms | Online Portal and in person support
Order and deliver compliance posters (cost of posters charged separately)
Assist with Exempt vs. Non-Exempt, overtime, etc.
Advise owner/manager on state and federal employment law and accepted practices which relate to any aspect of employment.
|  | Assist with terminations to ensure compliance | On-site assistance as needed
|  | Assist with compilation of 401k census data or FRS reporting and audit | No FRS, correct?
|  | Assist with compilation of census data for Section 125 Plan (Cafeteria Plan) | Census data needed would have to be specified
Staff onboarding - coordinates any new hire paperwork prior to start date and sends all required paperwork to Compliance Manager who will send it to the Sponsor
Notify all appropriate staff when a employee leaves the school
Notify all appropriate staff when a employee joins the school
Maintains and reports on Staff Roster
Maintains and distributes emergency contact list
Conduct Employee Benefit Enrollment Meeting
Shop benefit plans upon client's request to ensure that the best plans and rates are obtained
Set up payroll deductions for employee portion of benefits
Remove terminated employees from benefits plans in a timely manner
Order benefits information and keep client's supplies well stocked
Facilitate open enrollment for staff benefits
Ensure COBRA and HIPAA compliance through distribution of appropriate forms and memos to new hires, dependents, terminating employees or employees experiencing other qualifying events
Ensure 401k distribution paperwork is mailed to terminated employees
Compile benefit information to give to employees at the time of eligibility
Assist employees with 401k loans
Monthly: Distribute 401k termination and rollover documents to employees as needed
|  | Review performance evaluations prior to managers meeting with employees | Review to ensure compliance, not to provide input on performance FS 1012.34
|  | Create New Employee Application Package | ESI; May not need
Daily: Process verification of employment requests from lenders
Archive Drug Test Results in Employee Folders
Track New Employee Onboarding Status
Track New Employee Application Status
Provide monthly reports for owner/management regarding: Performance reviews due
Provide monthly reports for owner/management regarding: Birthdays
Manage employee leaves of absence (LOA) - including Family and Medical Leave Act. ADA
Complete documentation for any employee garnishments, notify employee and facilitate payroll deductions
Monthly: Monitor employee retirement and HSA accounts for annual limits
Monthly: Distribute 401(k) plan participant reports per plan rules
Process Unemployment Claims
Work with workers compensation carrier to close claims as quickly as possible
Handle workers compensation renewal process upon client's request to ensure that the best plans and rates are obtained
Facilitate quarterly safety meetings with employees
Assist in evaluating modified duty programs for employees with work-related injuries
Arrange workers compensation workplace audits to recommend safety improvements
Administer workers compensation claims
Act as point of contact for workers compensation adjusters and medical facilities to provide information and communicate concerns
Complete requests for appeal
Attend appeal hearings to present employers case
|  | Respond to any EDD follow up forms or phone calls | Note* Appeal to Florida Department of Economic Opportunity
Manage Teacher Certification Process
Maintain Staff List - Including Certifications and Teaching Assignments
Distribute Monthly reports to Mgt for Professional Development Status
|  | Maintain Teacher Certification backup in Folders | Electronic or Hardcopy
Create Manager Reference Guide
Create Illness Injury & Prevention Plan
Review all forms and documents for accuracy, dates, signatures, etc.
Record all disciplinary actions, performance reviews, salary increases, etc.
Input all employee documents into HRIS to be able to generate employee reports
Ensure I-9 information is complete and stored in separate files
Conduct monthly I-9 audit to ensure compliance
Ensure confidential medical information/doctors' notes are stored in separate files
|  | Create an employee file (paper and electronic) for each employee | ESI is 100% paperless but maintains 2 encrypted, compliant, separate digital file systems for guaranteed backup at all times
Weekly: Run bi-weekly payroll, including hourly and salaried employees
Daily: Per Employee requests, provide payroll data and/or payroll system login assistance
As Required: Process Part Time (Recess Monitoring Staff, etc.) payroll
Produce accurate, timely and customized financial statements each period that will allow the client an opportunity to thoroughly understand their numbers and profitability.
Process all payroll checks, direct deposits and payroll taxes on client's set labor period end and pay date schedule
Process 401k programs
Maintain employee payroll records and process all W2s at year end
Handle all worker's compensation audits on behalf of the client
Handle all benefit, vacation and PTO accruals
Financial Statements & Customized Reporting
Complete and file all quarterly payroll tax returns
Complete and file all employee garnishments, EDD requests
|  | Weekly: Pay bi-weekly payroll benefits: HSA accounts and 401k accounts | See notes above regarding 403b
|  | Create Employee Application Webpage | ESI; May not need
Provide input to Policies & Procedures
Setup Optima Portal to ESI system
Reach out to Local Colleges
|  | Staff Take Drug Tests | Review with Optima
Staff are Fingerprinted and cleared
Create Cal-OSHA and OSHA Compliant Safety Handbook
Setup and Configure Copiers
Install protective slides on all desks and/or chairs to protect floors
Monthly: Coordinate with Event Coordinator for any upcoming events
Manage Facility Vendors
Ensure staff Set up food for special events as necessary
As required: Purchase food for Teacher Lounges as necessary
As required: Purchase food for special events as necessary
Setup Stage/Chairs as required for special events
Review and advise of any issues with facility
Reset Stage/Chairs as required after special events
Manage HVAC Status Database
Maintain Storage Room Organization - TBD
Maintain Storage Room Organization - TBD
Maintain Storage Room Organization - TBD
|  | Maintain School Mini-Van: | Maintain School Mini-Van: 1. Oil changes 2. Washing 3. Vacuuming 4. Tire Air 5. Tire Rotations 6. Manufactures recalls
Maintain General organization of facilities; authorize changes as required.
Install/Maintain Student Parking Signs
Install School Van Parking Sign
Install Reserved Parking Signs
Coordinate and report on health and safety inspections to SOM
Coordinate and report Fire Inspections to SOM
|  | Conducts and Reports on Fire, Tornado and Lockdown Drills | Conducts and Reports on Fire, Tornado and Lockdown Drills 1. Coordinate with Assistant Principal 2. Call Vendor for test 3. Pull alarm 4. Reset system 5. Update Status Report (will submit to SOM at end of year)
Archive Fire Department, Fire Extinguishers, Health and Safety Inspection Reports
|  | Setup Cafeteria for Events | Turn down AC, etc.
|  | Misc. projects as they arise | Re-stringing flag pole, etc.
|  | Manage School Facility Improvement Program | Plan summer work
|  | Manage Security Surveillance System | Plan and Implement Security Plan
|  | Manage Facility Upgrade Requests | Facility Help Desk
Download MSDS sheets for all Hazards material
Report evidence of vandalism or student mistreatment of facilities to Assistant Principal
Obtain quotes for maintenance or repair work needed
Manage Facility Maintenance Issues (Facility Help Desk)
Coordinate repair and maintenance of HVAC system
Coordinate painting repairs
Coordinate irrigation repairs
Coordinate general upgrades (hanging bulletin boards, pictures etc.)
Coordinate electrical repairs
Assess brown out situations and contact FPL
|  | Remove Ex-Employees from Building Access System | Retrieve Key Fobs and room keys as required
|  | Enroll New Employees in Building Access System | Issue Key Fobs and room keys as required
Manage Facility Custodial Issues
Manage Facility Custodial Cleaning
Maintains Custodial service issue log of poor service
Maintain Janitors Closet Cleanliness - TBD
Ensure Staff Cleans up Kitchen after special events as necessary
|  | Coordinate Copier Repair | Work with Admin Assistant
Bi-Annually: Food Service Inspection Report
Coordinate plumbing repairs
Oversee custodial services and coordinates changes or adjustments in services per request
Clinic: Ordering supplies as needed (ice packs, band-aids, etc.)
Order staff coffee station supplies as needed
Order Restroom supplies as required
Order Cleaning supplies as required
Order Copier supplies as required
Weekly: Place food bulk orders for lunch
Request Checks for vendors
Print and analyze weekly sales reports and communicate with vendor if necessary
Pick up bulk order- milk (Usually Mondays)
Mondays and Thursdays- print order summary and place lunch orders with vendors
Assess organization of Food Service supplies
Assess inventory of Food Service supplies and place order if necessary
Monthly: Set menu for next month, send out email about menu and any changes
Monthly: Quick monthly meeting with lunch staff about sales, goals, brainstorm ideas
Monthly: Print sales report, compare to prior month, set goals and adjust menu, items for purchase, and schedules if necessary
Monthly: Maintain Lunch Menu on online system one month in advance
Print daily distribution report and absentee list
Prepare kitchen for lunch- dispose of leftovers past 2 days, set-up items for purchasing, accept lunches from vendor
Prepare cafeteria for lunch- wipe down and sanitize tables, restock disposables, restore tables, trash cans, and chairs to original spots
|  | Post lunch duties | Post lunch duties 1. Tally up items sold 2. Deposit cash with Finance 3. Prepare cash box for following day
Manage parent issues on lunch orders as necessary
Manage Lunch Room Staff
|  | Lunch | Lunch 1. Distribution of meals 2. Sell side items 3. Manage flow of cafeteria 4. Maintain decorum
Clean-up kitchen- wipe tables and counter top, date leftover food, re-stock, turn warmer off
Clean-up cafeteria- sweep, wipe tables
Breakfast- set up, clean-up, and re-stock
Manage parent e-mails re meals
Free and Reduced Price Meal Applications processing (Dup)
|  | 1. School Wellness Policy Team - Develop team | Refer to latest version of policy for details
|  | 1. School Wellness Policy Team - Meet annually (at least one time per year) | Refer to latest version of policy for details
|  | 1. School Wellness Policy Team - Send updated copy to the Florida Department of Agriculture and Consumer Services (FDACS) when a change or revision is made. | Refer to latest version of policy for details
|  | 1. School Wellness Policy Team - Ensure compliance with federal and state regulations for competitive food and beverage items sold on the school campus (7 CFR 210.11 and FAC 5P-1.003); | Refer to latest version of policy for details
|  | 1. School Wellness Policy Team - Maintain a school calendar identifying the dates when exempted competitive food fundraisers will occur in accordance with the frequency specified in paragraph (c) of FAC 5P-2.002; | Refer to latest version of policy for details
|  | 1. School Wellness Policy Team - Report school’s compliance of the regulations to the school principal/school operations manager | Refer to latest version of policy for details
|  | 1. School Wellness Policy Team - Assess wellness policy at least every three years following the triennial assessment | Refer to latest version of policy for details
|  | 2. School Wellness Policy - Nutrition Promotion | Refer to latest version of policy for details Review and consider evidence-based strategies and techniques in establishing goals for nutrition promotion and education, physical activity and other school-based activities that promote student wellness to include, at a minimum, a review of Smarter Lunchroom tools and techniques.
|  | 3. School Wellness Policy - Nutrition Education (Regularly 2019/Quarterly 2020) | Refer to latest version of policy for details Students receive quarterly nutrition education that is interactive and teaches skills they need to adopt healthy eating behaviors. Classroom lectures, activities and student participation are provided in nutrition and health classes.
|  | 3. School Wellness Policy - Nutrition Education (Annually) | Refer to latest version of policy for details The staff responsible for health/nutrition education will be adequately prepared and participate at least annually in professional development activities to effectively deliver an accurate nutrition education program as planned. Preparation and professional development activities will provide basic knowledge of nutrition combined with skill practice in program-specific activities and instructional techniques and strategies designed to promote healthy eating habits.
|  | 4. School Wellness Policy - Physical Activity | Refer to latest version of policy for details Ensure required PE requirements are scheduled accordingly
|  | 5. School Wellness Policy - Other School-Based Activities | Refer to latest version of policy for details
|  | 6. School Wellness Policy - Follow Guidelines for All F&B Available During the School Day | Refer to latest version of policy for details
|  | 7. School Wellness Policy - Follow Policy for F&B Marketing | Refer to latest version of policy for details
|  | 8. School Wellness Policy - Evaluation and Measurement of the Implementation of the Wellness Policy | Refer to latest version of policy for details
|  | 9. School Wellness Policy - Informing the Public | Refer to latest version of policy for details
|  | 10. School Wellness Policy - Community Involvement | Refer to latest version of policy for details
|  | 11. School Wellness Policy - Record Keeping | Refer to latest version of policy for details
Yearbook - Program Advisor and Coordination with company
|  | Plan and Implement Kindergarten Open House | Plan and Implement Kindergarten Open House 1. Add to calendar 2. Prepare Student Class sheets 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event Principal provides direction
|  | Obtain K-8 Progress Monitoring Login (previously known as FLKR) | SOMs - Do not be concerned about Florida Kindergarten Readiness Screenings until about mid-July. The Florida Kindergarten Readiness Screenings program was previously called the FLKR Program. However, the FLKR Program is no longer active. There is a new program that the FLDOE will be implementing for the 2022-2023 school year called the K-8 Progress Monitoring. This information was provided by Teri Williams at Teri.Williams@fldoe.org or 850-245-0804 from the contact us webpage. https://www.fldoe.org/accountability/assessments/k-12-student-assessment/flkrs/ Notes regarding FLKRS Program: FLKRS stands for Florida Kindergarten Readiness Screener. State law requires screening for all public school kindergarten students within the first 30 days of the school year. Kindergarten teachers use the results to help understand each child's readiness for school and plan lessons to meet individual needs. The purpose of the Florida Kindergarten Readiness Screener (FLKRS) is to gather information about a child's overall development and address each student's readiness for kindergarten based on the Florida Early Learning and Developmental Standards for Four-Year-Olds. http://www.fldoe.org/accountability/assessments/k-12-student-assessment/flkrs/
|  | Post required Human Resources notices in Teacher workrooms | Post required Human Resources notices in Teacher workrooms 1. Employee Rights under the Fair Labor Standards Act 2. Job Safety and Health: It&#x27;s the Law 3. Employee Rights and Responsibilities Under The Family and Medical Leave Act 4. Pay Transparency Nondiscrimination Provision (41 CFR Part 60-1.3
Setup Employment Posters on bulletin boards
Create Yearbook Program - Recruit Yearbook Manager/Producer
Manage execution of Florida Kindergarten Readiness (FLKR) Screener within the first 30 days of each school year.
Manage FLKR Testing
|  | Download and Create Uniform Assessment Calendar per Rule 6A-1.094224. Post on Website. | FS 1008.22 (7)(d) Rule: 6A-1.094224
Create and Maintain Detail FSA Test Plan
|  | Setting up and running 6th Grade Blue and Gold | Archive board approved minutes of meeting with list approval
Conduct FSA Pre-Test
|  | Prepare and Test Technology for FSA Pre-Test | Annually
|  | Identify Student EOC Testing Requirements | Work with Upper School Dean
Coordinating Movies Nights for 3rd through 12th grade
|  | Manage Planning School Website Event Calendar | Manage Planning School Website Event Calendar 1. Maintain Database of prior year events 2. Create plan of next year&#x27;s events 3. Update projected events months ahead of time
|  | Manage School Picture Program | Manage School Picture Program 1. Picture taking day 2. Senior Picture taking day 3. Retake days 4. Class pictures 5. Select and contract with Picture Company
Manage school website event calendar - Form for event completed by requester
Manage school website event calendar- Verify dates
|  | Plan and Implement 1st through 6th Grade Open House | Plan and Implement 1st through 6th Grade Open House 1. Add to calendar 2. Prepare Student Class sheets 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event Principal provides direction
|  | Planning and Implementing Field Trips | Planning and Implementing Field Trips 1. Working with staff to plan 2. Working with outside agents to plan 3. Estimating Costs/Obtaining Approval of Cost/Revenue Estimates 4. Marketing with parents and students 5. Obtaining Student/Parent Payment/Approval Forms 6. Coordinating Transportation and Facility Use 7. Coordinating Volunteers Principal provides direction
|  | Setting up and running Staff vs students sports events | Principal provides direction
Supporting Talent Show Grades 5-12
Supporting Talent Show Grades K-4
Approve Facility Reservation Request on School Website backend
Deliver incoming items for Reception
Deliver material to Staff mailboxes when needed
Help in Dismissal process when they need extra hands
|  | Mailings | 1. Delivery of mail"
|  | Manage Lost and Found | Manage Lost and Found 1. Organize and monitor Lost and Found Bin 2. Process Found Books and School Supplies 3. Process Found Uniforms (notify parents if possible) 4. Process Found Lunch Boxes and Water Bottles 5. Cycle Unclaimed Uniforms into Uniform Assistance Program at end of year. 6. Clean-out lost and found cart weekly
|  | Manage Uniform Assistance Program | Manage Uniform Assistance Program 1. Process Lost and Donated Uniforms 2. Storing items in Uniform Closet 3. Keep Uniform room organized 4. Assist parents that require and qualify for Uniform Assistance 5. Needy families on free/reduced lunch, if requested 6. New parents that come in at the last minute
|  | Manage Afternoon Car Line | Manage Afternoon Car Line 1. Set up cones 2. Additional preparations a. Check microphones for batteries b. Umbrellas if needed c. Additional mats if rain 3. Cover areas that need additional assistance
Manage Lunch Room Volunteers
|  | Manage Recess Duty | Manage Recess Duty 1. Maintain and adjust recess monitor schedule 2. People in correct assigned areas 3. Discuss issues with Assistant Principal 4. Cover areas that need additional assistance 5. Work with monitors to ensure proper recess coverage
Recess Monitor - Organizing supplies after recess
Recess Monitor - Stock Recess nursing kit for minor first aid
|  | Manage the Substitute Program Part 1 | Manage the Substitute Program Part 1 1. Coordinate Subs 5AM to 8AM 2. Coordinate Subs 4PM to 9PM 3. Post Sub status on Sub Calendar 4. Create Sub Binder Templates for Teacher Use 5. Prepare Substitute Program at beginning of year (7 August to 16 August) 6.Verify readiness of Substitute Binders
|  | Manage the Substitute Program Part 2 | Manage the Substitute Program part 2 1. Notify appropriate staff of Split Classes 2. Keep Staff Absence Calendar Updated to reflect Teacher PTO and Sick Status 3. Create and maintain Sub Training Program and documentation 4. Onboard and coordinate training for subs 5. Facilitate obtaining a sub for faculty that is ill or on PTO 6. May include making copies or running down lesson plans from colleagues 7. Need to ensure sub is prepared and students have relevant lessons 8. Supervise students for short periods of time if sub or teacher needs to step out Principal provides direction
|  | Plan and Implement Upper School Open House | Plan and Implement Upper School Open House 1. Add to calendar 2. Prepare Student Class sheets 3. Notify parents 4. Plan staff participation 5. Coordinate Facility usage 6. Conduct event Principal provides direction
Plan Graduation
Plan Prom
|  | Club Coordination | Club Coordination: 1. Obtain Teacher commitment for clubs (Principal approves) 2. Obtain Management approval for Club ideas 3. Setup Webpage for Clubs. 4. Setup Form for club applications 5. Create Club Budget Projections for next year
Manage FSA Testing
|  | Supplies: Summer assistance | Supplies: Summer assistance 1. Inventory Office, Classroom & Science supplies 2. Supply order assistance 3. Deliver classroom supplies to classrooms
|  | Supplies: Manage Science Supplies | Supplies: Manage Science Supplies 1. Place Orders as needed 2. Counting/ sorting by teacher 3. Deliver to classroom 4. Reorder needed supplies 5. Keep store room in order
|  | Supplies: Manage Office Supplies | Supplies: Manage Office Supplies 1. Place Orders as needed 2. Counting/ sorting by teacher 3. Stock in store room 4. Keep store room in order
|  | Supplies: Manage Classroom Supplies | Supplies: Manage Classroom Supplies 1. Place Orders as needed 2. Counting/ sorting by teacher 3. Deliver to classroom 4. Reorder needed supplies 5. Keep store room in order
Recess Monitor - Requesting replacement supplies from Purchasing
|  | Various assigned projects | Various assigned projects 1. Sign Up Genius event setup 2. Collection and balancing of checks and/or cash for different event 3. Fundraisers 4. Car decals 5. Book replacement fees, 6. binding projects, laminating projects, etc.
Update SIS with Parent Email updates
Turn Lights out upon exit
Receive and process deliveries; Notify Admin for delivery
Process Tardies
Process Early dismissals
|  | Manage Volunteer program | Manage Volunteer program 1. Process Level 2 forms 2. Manage Level 2 status
Manage Visitors
Manage authorized pick-up changes
Maintain Front office cleanliness
|  | Mailings | Mailings 1. Prepare envelopes and letters
Lock Front Doors upon exit
Help preparing letters going home
Help preparing interims/report cards
|  | Greet and assist walk ins | Greet and assist walk ins 1. Check in volunteers 2. Early release of students 3. Answer general questions 4. Drop off of lunches
Family information updates in SIS - phone number changes, authorized pick up changes, email changes, etc.
Entering absences in School SIS and Sponsor SIS
Create and distribute Car line tags
Check voicemails
Attendance updates in SIS - tardies, excused appointments, excused absences, early dismissal, etc.
Answer phone in friendly and helpful manner
After school care (Late Pickup)
|  | Process late Pickups | Charge Fee; Reminder for Fee
Clinic: Staff Nurse's station/Clinic (Non-Medical Assistant - need 2)
|  | Clinic: Back up Nursing | Daily and Administer meds as NMA
Clinic: Back Up Nursing - Training
Read, review and forward or answer all mail to the general information email account
Read, review and answer emails from staff and parents.
Notifying Principal about red flags for tardies, Absences and early dismissals
Email family with repeated Tardy offenses
Contact parents to pick up students who need to go home due to behavior
Communicate with Registrar regarding attendance and coordination of School SIS information with Sponsor SIS information
|  | Configure Sponsor SIS (Focus) | Enter all student schedules, bells, and periods in District SIS from School SIS or what Enrollment Manager provides. (Yearly maintenance and can be changed at any given time with new hires or ESE services)
Support FLKR Testing - Get "Florida Student Number" from Focus for K Students
|  | Archive October Survey Items for possible Audit: | Rule: 6A-1.0503 (3) Archive October Survey Items for possible Audit: - Copy of final FTE report showing individual student schedules and reported FTE - Daily attendance documentation (signed and dated by teachers and principal) - Transportation attendance records (signed and dated by bus drivers) or ridership verification form for students using public transportation
|  | Archive October Survey Items for possible Audit: | Copy of final FTE report showing individual student schedules and reported FTE Daily attendance documentation (signed and dated by teachers and principal) Transportation attendance records (signed and dated by bus drivers) or ridership verification form for students using public transportation
|  | Archive February Survey Items for possible Audit: | Rule: 6A-1.0503 (3) Archive February Survey Items for possible Audit: - Copy of final FTE report showing individual student schedules and reported FTE - Daily attendance documentation (signed and dated by teachers and principal) - Transportation attendance records (signed and dated by bus drivers) or ridership verification form for students using public transportation
|  | Archive February Survey Items for possible Audit: | Copy of final FTE report showing individual student schedules and reported FTE Daily attendance documentation (signed and dated by teachers and principal) Transportation attendance records (signed and dated by bus drivers) or ridership verification form for students using public transportation
|  | Process Student Enrollment/Withdrawals | Any given time. This is usually high beginning, mid year and end of year
Deal with enrollment questions/issues
Process registration documents during enrollment
|  | FTE staff reporting (3 times a year Oct, Feb, and August) | May duplicate some other reporting
|  | Submit to Sponsor: Violations of the Code | Collier 3.M Monthly Submit to Sponsor: The School will report each month to the District the number of violations of the Code, by offense, to be included in the Districts discipline reporting, as required by law.
Manage Enrollment/Registration database
|  | FLVS/Sponsor SIS: | 1. Inputting grades when students withdraw 2. Inputting grades when students complete FLVS 3. Inputting Grades when students transfer into our school 4. Inputting end of year grades
Maintain Sponsor Student Information System
Manage Elementary School Confirmed/Withdrawal student status
Record keeping for all students (Daily...this is anything from updating address, phone numbers, immunizations, physicals, test scores such as CELLA/WEDA for ELL students, guardianship, filing etc...)
Submit: FTE Records Signed by Administrator
Submitting Attendance from School SIS into Sponsor SIS (Daily)
Update SIS with schedule and student info
Create, send and process Upper School "Intent to Return" forms
Create Lotteries in Lottery system Mid December
Create, send and process Elementary School "Intent to Return" forms
Manage Upper School Confirmed/Withdrawal student status
Plan number of open seats
Process Records request from schools and to schools. (Usually review records to better assist admin)
Run Lotteries as required
Support Registration Process
Update and post Registration packet to website
Free and Reduced Price Meal Applications processing (Dup)
|  | Clinic: Back up Nursing | Administer meds as NMA
Clinic: Back Up Nursing - Training
Clinic: Assist sick, upset and/or injured kids
Clinic: Call Parents - To pick up sick students
Clinic: Call Parents based on the type of injury as needed
Clinic: Courtesy calls to parent if student complains or-noticeable bump or injury
Clinic: Fill in Clinic Log- paper and on Sponsor SIS
Clinic: Perform and document Temp checks
Clinic: Staff Nurse's station/Clinic (Non-Medical Assistant - need 2)
At end of day go to classrooms to hand out Transportation changes if Classroom Assistants are not available
Collect returned Report Card envelopes
Help Receptionist check in late students
Hunt for students if Receptionist can't get a hold of a teacher in the classroom
Provide assistance to admin as needed on a daily bases (Principal, Student Services)
Receptionist backup
Send out 6th Grade TDAP emails to issue parents in May
|  | Support Tracking 7th Grade TDAP Immunization forms | http://www.floridahealth.gov/programs-and-services/immunization/children-and-adolescents/school-immunization-requirements/index.html#seventhGrade Additional Immunization Requirements for 7th Grade Entry Effective with 2009–2010 school year (then an additional grade is added each year thereafter), in addition to compliance with all other immunization requirements, children entering, attending, or transferring to the seventh grade in Florida schools must complete the following: One Tetanus-diphtheria-acellular pertussis (Tdap) See the http://www.floridahealth.gov/programs-and-services/immunization/children-and-adolescents/_documents/school-guide.pdf* for complete information on school requirements.
Generate Report cards
Help preparing interim reports/report cards
Provide Report Cards to Teachers
Track MIP in Status Report, collect paperwork and email to Sponsor
|  | All permanent (Category A) records of students leaving the School, whether by graduation, transfer to another public school, or withdrawal to attend another school, will be immediately transferred to the Sponsor in accordance with Florida Statutes. Records will be transmitted to the Sponsor�s records retention department. | Collier 3.H.3
|  | Records of student progress (Category B) will be transferred to the appropriate school if a student withdraws to attend another public school or any other school. The School may retain copies of the departing student�s academic records created during the student�s attendance at the School. | Collier 3.H.4
|  | Student Records Maintenance | Collier 3.H.5 Upon the withdrawal of a student from the School, the School will retain the students original records, except that such records will be immediately transferred to another Sponsor school when requested by that school. Requests for student records from public or private schools outside of the County and private schools within the County must be made in writing. Only copies of requested records may be provided. Copies only of student records may be provided to parents upon their request unless the student is considered an eligible student under FERPA. The School will retain the students record for three (3) years after student withdrawal or until requested by another Sponsor public school in this County, whichever comes first. At the end of the third year all inactive student records will be returned to the Sponsors records retention department.
Provide parent email list for Constant Contact uploads
|  | Maintain Summary Information for distribution as requested | see chuck for template
Track and submit to Sponsor MIP annually for teachers
|  | Correspond with parents | Almost daily regarding grades, testing, assisting admin or teachers etc.
Communicate with Sponsor when it comes to student demographics, ELL, ESE, Staff Reporting, Scheduling, and 504's
Contacting parents with attendance issues (weekly)
Correspond with FLVS transcript request for students who have enrolled in FLVS
Enter Discipline Pink Slips into Sponsor SIS as Referrals
Enter Grades into Sponsor SIS from report cards
Enter Suspensions into Sponsor SIS as Referrals
ESE, 504, and ELL data inputting (2-3 time a week sometime in batches of 5 or more students at a time. Paperwork is provided by Student Services
Setup and Configure Wi-Fi system
Setup and Configure Switches
Setup and Configure Staff Microsoft Office
Setup and Configure Staff G-Suite Email system
Setup and Configure Staff Computers - UPS
Setup and Configure Staff Computers - Laptops
Setup and Configure Staff Computers - iPads
Setup and Configure Staff Computers - Desktops
Setup and Configure Servers
Setup and Configure Security: Virus Protection
Setup and Configure Security: Patching Process
Setup and Configure Security: Internal Security
Setup and Configure Public Address System
Setup and Configure Office Fax/Monochrome Printers
Setup and Configure Office Color Printers
Setup and Configure Office Check Printers
Setup and Configure Internet Access
Setup and Configure Hardware Server (Authentication, Print Server, etc.)
Setup and Configure G-Suite Users
Setup and Configure G-Suite Data Storage
|  | Setup and Configure FSA Laptops | Need for FLKRS
Setup and Configure Classroom Projectors
|  | Setup and Configure Classroom Monochrome Printers | If provided
Setup and Configure Car Line Sound System
Setup and Configure Cameras -Hallway
Setup and Configure Cameras - Server software
Setup and Configure Cameras - External
Setup and Configure Camera - Hardware
|  | Setup and Configure Cafeteria Stage Lighting | If we have a stage
|  | Setup and Configure Cafeteria Sound System | If we have one.
Setup and Configure Cafeteria Projector
Setup and Configure VOIP phone System
Setup and Configure Security: Password Policies
Manage Wi-Fi system
Manage VOIP Phone System
Manage Switches
Manage Staff G-Suite Email system
Manage Staff Computers - UPS
Manage Staff Computers - Laptops
Manage Staff Computers - iPads
Manage Staff Computers - Desktops
Manage Servers
Manage Server Room organization - TBD
Manage Security: Virus Protection
Manage Security: Patching Process
Manage Security: Internal Security
Manage Security: Content Filtering
Manage Public Address System
Manage Office Fax/Monochrome Printers
Manage Office Color Printers
Manage Office Check Printers
Manage Network Issues
Manage Microsoft Office 365 for entire staff
Manage Internet Access
Manage Hardware Server (Authentication, Print Server, etc.)
Manage G-Suite Vault
Manage G-Suite Users
Manage G-Suite Data Storage
Manage testing Laptops
Manage Connectivity Issues
Manage Classroom Projectors
Manage Classroom Monochrome Printers
Manage Car Line Sound System
Manage Cameras -Hallway
Manage Cameras - Server software
Manage Cameras - Server Hardware
Manage Cameras - External
Manage Cafeteria Stage Lighting
Manage Cafeteria Sound System
Manage Cafeteria Projector
Setup and Configure Application: Visitor Screening